## Cover page
DMS-FT-520
Digital Engineering Project Data Schema
Scheduling Schema
Version | 1.0
Issued date: | October 2019
Important Warning
This document is one set of standards developed solely and specifically for use on Transport Assets (as defined in the Asset Standards Authority Charter). It is not suitable for any other purpose. The copyright and any other intellectual property in this document will at all times remain the property of the State of New South Wales (Transport for NSW). You may not use or adapt this document or rely upon it in any way unless you are providing products or services to a NSW Government agency and that agency has expressly authorised you in writing to do so. If this document forms part of a contract with, or is a condition of approval by a NSW Government agency, use of the document is subject to the term of the contract or approval. To be clear, the content of this document is not licensed under any Creative Commons Licence. This document may contain third party material. The inclusion of third party material is for illustrative purposes only and does not represent an endorsement by NSW Government of any third party product or service. If you use this document or rely upon it without authorisation under these terms, the State of New South Wales (including Transport for NSW) and its personnel does not accept any liability to you or any other person for any loss, damage, costs and expenses that you or anyone else may suffer or incur from your use and reliance on the content contained in this document. Users should exercise their own skill and care in the use of the document. This document may not be current and is uncontrolled when printed or downloaded. Standards may be accessed from the Digital Engineering Framework website at:
www.transport.nsw.gov.au/digitalengineering

## Preface
Scheduling Schema
|  | Version | 1.0
|  | Issued date: | October 2019
Preface
Transport for New South Wales (TfNSW) is developing the Digital Engineering (DE) Framework to enable time, cost and quality improvements to the way that projects are planned, designed, constructed, operated and maintained throughout their lifecycle. DE processes will provide TfNSW with an approach that enables digital information to become a key enabler of stakeholder engagement, decision making, improved asset knowledge, capability and capacity planning. Implementing and adhering to this vision will enable individuals, who are responsible for the delivery and management of TfNSW’s assets, to make more informed decisions. The DE Framework is yet to be delivered, and is currently in the early ‘Interim Approach’ stage of the program. This document should be read in conjunction with all related DE Framework Interim Approach documentation. Any application of the DE Framework Interim Approach or any of its parts must be considered in a project-specific context. Adoption of the DE Framework should be undertaken in consultation with the DE Team to ensure best appropriate practice.

## Standard governance
DMS-FT-520
Scheduling Schema
1.0
October 2019
Standard governance
Owner: | Workstream Specialists
Authoriser: | Digital Engineering Program Manager
Approver: | Director Digital Engineering
Document history
Version | Summary of Changes
1.0 | First issue, DE Framework Release 3
For queries regarding this document,
please email the Digital Engineering team at
Digital.engineering@transport.nsw.gov.au
or visit www.transport.nsw.gov.au/digitalengineering

## Instructions
Instructions
# | Instructions
01 | Extending Work Packages A Contractor may define more granular work packages and reference those work packages. However, these MUST be children of the Work Packages defined by TfNSW. The naming convention for the Work Packages Code is: [Project code].[Project Phase Code].[Work Package Group Code].[Work Package Type Code].[Location Code].### e.g. TfNSW provided work package code: ST1.PLD.WG03.WT2.DES.001 Contractors wishing to create child work packages should copy the TfNSW provided Work Package Code and a "." followed by a number. e.g. Contractor child work package code: ST1.PLD.WG03.WT2.DES.001.001 Refer to the Work Packages Type tab for all Work Package Type Codes. Note, these must be kept in synch with the Project Data Building Blocks (PDBB) managed by TfNSW.
02 | P6 Activity Codes The "Work Packages" tab in this schema provides a list of all "Design", "Construction", "Commissioning" and "Supply" Work Packages. When creating Project Activity Codes in P6, following this mapping approach: - P6 Activity Code maps to the Work Package Code - P6 Activity Code Description maps to the Work Package Name

## Work Packages
WORK PACKAGES
Activity Code | Activity Name
Work Package Code | Work Package Name | Work Package Type | Work Package Group
ST1.PLD.WG03.WT01.DES.001 | Station Upgrade Architecture Concept | WG03.WT01 - Feasibility Design | WG03 - Design
ST1.PLD.WG03.WT02.DES.001 | Station Upgrade Technical Services | WG03.WT02 - Preliminary Design | WG03 - Design
ST1.PLD.WG03.WT02.DES.002 | Station Upgrade Services Design | WG03.WT02 - Preliminary Design | WG03 - Design
ST1.IDA.WG07.WT01.DES.001 | Supply of Parts | WG07.WT01 - TfNSW Supply | WG07 - Supply
ST1.DEL.WG08.WT01.DES.001 | Early Works | WG08.WT01 - Temporary Works | WG08 - Construction
ST1.DEL.WG08.WT02.DES.001 | Construction Set 1 | WG08.WT02 - Substructure | WG08 - Construction
ST1.DEL.WG08.WT03.DES.001 | Construction Set 2 | WG08.WT03 - Superstructure | WG08 - Construction
ST1.DEL.WG09.WT01.DES.001 | Commissions of System Set 1 | WG09.WT01 - System Commissioning | WG09 - Commissioning
ST1.DEL.WG09.WT01.DES.002 | Commissions of System Set 2 | WG09.WT01 - System Commissioning | WG09 - Commissioning
ST1.DEL.WG09.WT01.DES.003 | Commissions of System Set 3 | WG09.WT01 - System Commissioning | WG09 - Commissioning
ST1.DEL.WG09.WT02.DES.001 | Asset Information Handover | WG09.WT02 - Handover | WG09 - Commissioning

## Work Package Types
Work Package Group | Work Package Group ID | Work Package Type Code | Work Package Type Description | Work Package Type Display
WG01 - Project Management | WG01 | WG01.WT1 | Project Management (Other) | WG01.WT1 - Project Management (Other)
WG01 - Project Management | WG01 | WG01.WT2 | Safety Management | WG01.WT2 - Safety Management
WG01 - Project Management | WG01 | WG01.WT3 | Legal | WG01.WT3 - Legal
WG01 - Project Management | WG01 | WG01.WT4 | Commercial | WG01.WT4 - Commercial
WG01 - Project Management | WG01 | WG01.WT5 | Human Resources | WG01.WT5 - Human Resources
WG01 - Project Management | WG01 | WG01.WT6 | Stakeholder Management | WG01.WT6 - Stakeholder Management
WG01 - Project Management | WG01 | WG01.WT7 | Audit | WG01.WT7 - Audit
WG01 - Project Management | WG01 | WG01.WT8 | etc | WG01.WT8 - etc
WG02 - Site Investigations (initial) | WG02 | WG02.WT1 | Geotechnical | WG02.WT1 - Geotechnical
WG02 - Site Investigations (initial) | WG02 | WG02.WT2 | Contamination | WG02.WT2 - Contamination
WG02 - Site Investigations (initial) | WG02 | WG02.WT3 | Survey | WG02.WT3 - Survey
WG02 - Site Investigations (initial) | WG02 | WG02.WT4 | Noise Monitoring/Study | WG02.WT4 - Noise Monitoring/Study
WG02 - Site Investigations (initial) | WG02 | WG02.WT5 | Flood Monitoring/Study | WG02.WT5 - Flood Monitoring/Study
WG02 - Site Investigations (initial) | WG02 | WG02.WT6 | Heritage Study | WG02.WT6 - Heritage Study
WG03 - Design | WG03 | WG03.WT1 | Feasibility Design | WG03.WT1 - Feasibility Design
WG03 - Design | WG03 | WG03.WT2 | Preliminary Design | WG03.WT2 - Preliminary Design
WG03 - Design | WG03 | WG03.WT3 | Concept Design | WG03.WT3 - Concept Design
WG03 - Design | WG03 | WG03.WT4 | Detailed Design | WG03.WT4 - Detailed Design
WG03 - Design | WG03 | WG03.WT5 | Works as Executed (WAE) Design | WG03.WT5 - Works as Executed (WAE) Design
WG04 - Property | WG04 | WG04.WT1 | Property Services | WG04.WT1 - Property Services
WG04 - Property | WG04 | WG04.WT2 | Acquisition | WG04.WT2 - Acquisition
WG04 - Property | WG04 | WG04.WT3 | Relocation Costs | WG04.WT3 - Relocation Costs
WG04 - Property | WG04 | WG04.WT4 | Environmental Protection & Offsets | WG04.WT4 - Environmental Protection & Offsets
WG05 - Environmental Assessment | WG05 | WG05.WT1 | Environmental Impact Statement | WG05.WT1 - Environmental Impact Statement
WG05 - Environmental Assessment | WG05 | WG05.WT2 | Planning Approval | WG05.WT2 - Planning Approval
WG06 - Preliminaries | WG06 | WG06.WT1 | Mobilisation | WG06.WT1 - Mobilisation
WG06 - Preliminaries | WG06 | WG06.WT2 | Demobilisation | WG06.WT2 - Demobilisation
WG06 - Preliminaries | WG06 | WG06.WT3 | Offices & Buildings | WG06.WT3 - Offices & Buildings
WG06 - Preliminaries | WG06 | WG06.WT4 | Office Management & Admin | WG06.WT4 - Office Management & Admin
WG06 - Preliminaries | WG06 | WG06.WT5 | Fees & Notices | WG06.WT5 - Fees & Notices
WG06 - Preliminaries | WG06 | WG06.WT6 | Insurances | WG06.WT6 - Insurances
WG06 - Preliminaries | WG06 | WG06.WT7 | Guarantees & Warranties | WG06.WT7 - Guarantees & Warranties
WG06 - Preliminaries | WG06 | WG06.WT8 | Possession Management | WG06.WT8 - Possession Management
WG06 - Preliminaries | WG06 | WG06.WT9 | Traffic Management | WG06.WT9 - Traffic Management
WG06 - Preliminaries | WG06 | WG06.WT10 | Plant & Equipment | WG06.WT10 - Plant & Equipment
WG06 - Preliminaries | WG06 | WG06.WT11 | Demolition | WG06.WT11 - Demolition
WG06 - Preliminaries | WG06 | WG06.WT12 | Other Preliminaries | WG06.WT12 - Other Preliminaries
WG07 - Supply | WG07 | WG07.WT1 | TfNSW Supply | WG08.WT1 - Temporary Works
WG08 - Construction | WG08 | WG08.WT1 | Temporary Works | WG08.WT2 - Substructure
WG08 - Construction | WG08 | WG08.WT2 | Substructure | WG08.WT3 - Superstructure
WG08 - Construction | WG08 | WG08.WT3 | Superstructure | WG08.WT4 - Finishes
WG08 - Construction | WG08 | WG08.WT4 | Finishes | WG08.WT5 - Fittings
WG08 - Construction | WG08 | WG08.WT5 | Fittings | WG08.WT6 - Internal Services
WG08 - Construction | WG08 | WG08.WT6 | Internal Services | WG08.WT7 - External Services
WG08 - Construction | WG08 | WG08.WT7 | External Services | WG08.WT8 - Equipment
WG08 - Construction | WG08 | WG08.WT8 | Equipment | WG08.WT9 - Composite Rates TBD
WG08 - Construction | WG08 | WG08.WT9 | Composite Rates TBD | WG09.WT1 - System Commissioning
WG09 - Commissioning & Handover | WG09 | WG09.WT1 | System Commissioning | WG09.WT2 - Handover
WG09 - Commissioning & Handover | WG09 | WG09.WT2 | Handover | WG10.WT1 - Defects Liability
WG10 - Finalisation | WG10 | WG10.WT1 | Defects Liability | WG07.WT1 - TfNSW Supply

## Scope WP (Design)
SCOPE WORK PACKAGE
Design Work Package
Ss only
Work Package Name | Project Location Code | Technical Discipline Code | Uniclasss 2015 Asset Code | Uniclasss 2015 Asset Title | Contract Code | Contract Description
ST1.PLD.WG03.WT01.DES.001 - Station Upgrade Architecture Concept | DES | AR | Ss_20_10_70_62 | People shelter systems | LRS ST1DC1 | Design Contract 1
ST1.PLD.WG03.WT01.DES.001 - Station Upgrade Architecture Concept | DES | AR | Ss_40_20_30_28 | External furniture systems | LRS ST1DC1 | Design Contract 1
ST1.PLD.WG03.WT01.DES.001 - Station Upgrade Architecture Concept | DESPLA | AR | Ss_30_10_60 | Panel roof structure systems | LRS ST1DC1 | Design Contract 1
ST1.PLD.WG03.WT01.DES.001 - Station Upgrade Architecture Concept | DESPLAP01 | AR | Ss_25_50_75 | Screen systems | LRS ST1DC1 | Design Contract 1
ST1.PLD.WG03.WT01.DES.001 - Station Upgrade Architecture Concept | DESPLAP02 | AR | Ss_25_50_75 | Screen systems | LRS ST1DC1 | Design Contract 1
ST1.PLD.WG03.WT02.DES.001 - Station Upgrade Technical Services | DES | EL | Ss_70_80 | Lighting systems | LRS ST1DC2 | Design Contract 2
ST1.PLD.WG03.WT02.DES.001 - Station Upgrade Technical Services | DES | TE | Ss_75_10_68 | Public communications systems | LRS ST1DC2 | Design Contract 2
ST1.PLD.WG03.WT02.DES.002 - Station Upgrade Services Design | DES | TE | Ss_75_90 | Ticket management systems | LRS ST1DC1 | Design Contract 1

## Scope of WP (Construction)
SCOPE WORK PACKAGE
Construction Work Package
Work Package Name | Project Location Code | Project Asset Code | Asset Description | Technical Discipline Code | Uniclasss 2015 Asset Code | Uniclasss 2015 Asset Title | Contract Code | Contract Description
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DES | FUR | AR | Street Furniture System | Ss_40_20_30_28 | External furniture systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DES | LIT | EL | Lighting System | Ss_70_80 | Lighting systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DES | PIS | TE | Passenger Information System | Ss_75_10_68 | Public communications systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DES | PSS | AR | People Shelter System | Ss_20_10_70_62 | People shelter systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLA | CNP01-1 | AR | Canopy | Ss_30_10_60 | Panel roof structure systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | BEN01-1 | AR | Bench - Type 1 | Pr_40_50_12_07 | Benches | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | BIN01-1 | AR | Waste bin - General Waste | Pr_40_50_07_77 | Segregated waste bins | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-1 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-2 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-3 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-4 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-5 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-6 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-7 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-8 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT01-9 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-1 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-2 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-3 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-4 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-5 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-6 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-7 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | LIGHT02-8 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | POST01-1 | AR | Sign Post Type 1 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | POST01-2 | AR | Sign Post Type 1 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | POST02-1 | AR | Sign Post Type 2 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | POST03-1 | AR | Sign Post Type 3 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP01 | SCN01-1 | AR | Wind Break Screen - Type 1 | Ss_25_50_75 | Screen systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | BEN01-3 | AR | Bench - Type 1 | Pr_40_50_12_07 | Benches | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | BEN01-4 | AR | Bench - Type 1 | Pr_40_50_12_07 | Benches | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | BIN01-2 | AR | Waste bin - General Waste | Pr_40_50_07_77 | Segregated waste bins | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-10 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-11 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-12 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-13 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-14 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-15 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-16 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-17 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT01-18 | EL | Recessed Downlight - Type 1 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-10 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-11 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-12 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-13 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-14 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-15 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-16 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | LIGHT02-9 | EL | Recessed Downlight - Type 2 | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | POST03-2 | AR | Sign Post Type 3 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | POST03-3 | AR | Sign Post Type 3 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | POST04-1 | AR | Sign Post Type 4 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | POST04-2 | AR | Sign Post Type 4 | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT02.DES.001 - Construction Set 1 | DESPLAP02 | SCN01-2 | AR | Wind Break Screen - Type 1 | Ss_25_50_75 | Screen systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT03.DES.001 - Construction Set 2 | DES | OPL | TE | Opal system | Ss_75_90 | Ticket management systems | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT03.DES.001 - Construction Set 2 | DESPLA | TKT01-1 | TE | Opal top up machine | Pr_40_70_22_88 | Ticket dispensers | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT03.DES.001 - Construction Set 2 | DESPLAP01 | CARD01-1 | TE | Opal Card Reader | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT03.DES.001 - Construction Set 2 | DESPLAP01 | CARD01-2 | TE | Opal Card Reader | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT03.DES.001 - Construction Set 2 | DESPLAP02 | CARD01-3 | TE | Opal Card Reader | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works
ST1.DEL.WG08.WT03.DES.001 - Construction Set 2 | DESPLAP02 | CARD01-4 | TE | Opal Card Reader | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works

## Scope of WP (Commissioning)
SCOPE WORK PACKAGE
Commissioning Work Package
Work Package Name | Location Code | Project Asset Code | Asset Description | Technical Discipline Code | Uniclasss 2015 Asset Code | Uniclasss 2015 Asset Title | Contract Code | Contract Description
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DES | FUR | Street Furniture System | AR | Ss_40_20_30_28 | External furniture systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DES | PIS | Passenger Information System | TE | Ss_75_10_68 | Public communications systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DES | PSS | People Shelter System | AR | Ss_20_10_70_62 | People shelter systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLA | CNP01-1 | Canopy | AR | Ss_30_10_60 | Panel roof structure systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP01 | BEN01-1 | Bench - Type 1 | AR | Pr_40_50_12_07 | Benches | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP01 | BIN01-1 | Waste bin - General Waste | AR | Pr_40_50_07_77 | Segregated waste bins | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP01 | POST01-1 | Sign Post Type 1 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP01 | POST01-2 | Sign Post Type 1 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP01 | POST02-1 | Sign Post Type 2 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP01 | POST03-1 | Sign Post Type 3 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP01 | SCN01-1 | Wind Break Screen - Type 1 | AR | Ss_25_50_75 | Screen systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | BEN01-3 | Bench - Type 1 | AR | Pr_40_50_12_07 | Benches | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | BEN01-4 | Bench - Type 1 | AR | Pr_40_50_12_07 | Benches | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | BIN01-2 | Waste bin - General Waste | AR | Pr_40_50_07_77 | Segregated waste bins | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | POST03-2 | Sign Post Type 3 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | POST03-3 | Sign Post Type 3 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | POST04-1 | Sign Post Type 4 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | POST04-2 | Sign Post Type 4 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.001 - Commissions of System Set 1 | DESPLAP02 | SCN01-2 | Wind Break Screen - Type 1 | AR | Ss_25_50_75 | Screen systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DES | LIT | Lighting System | EL | Ss_70_80 | Lighting systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DES | OPL | Opal system | TE | Ss_75_90 | Ticket management systems | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-1 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-2 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-3 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-4 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-5 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-6 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-7 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-8 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT01-9 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-1 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-2 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-3 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-4 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-5 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-6 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-7 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP01 | LIGHT02-8 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-10 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-11 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-12 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-13 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-14 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-15 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-16 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-17 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT01-18 | Recessed Downlight - Type 1 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-10 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-11 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-12 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-13 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-14 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-15 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-16 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.002 - Commissions of System Set 2 | DESPLAP02 | LIGHT02-9 | Recessed Downlight - Type 2 | EL | Pr_70_70_48_24 | Downlights | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.003 - Commissions of System Set 3 | DESPLA | TKT01-1 | Opal top up machine | TE | Pr_40_70_22_88 | Ticket dispensers | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.003 - Commissions of System Set 3 | DESPLAP01 | CARD01-1 | Opal Card Reader | TE | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.003 - Commissions of System Set 3 | DESPLAP01 | CARD01-2 | Opal Card Reader | TE | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.003 - Commissions of System Set 3 | DESPLAP02 | CARD01-3 | Opal Card Reader | TE | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works
ST1.DEL.WG09.WT01.DES.003 - Commissions of System Set 3 | DESPLAP02 | CARD01-4 | Opal Card Reader | TE | Pr_75_75_27_80 | Smart card readers and writers | LRS ST1MWS | Main Works

## Scope of WP (Supply)
SCOPE WORK PACKAGE
Supply Work Package
Work Package Name | Location Code | Project Asset Code | Asset Description | Technical Discipline Code | Uniclasss 2015 Asset Code | Uniclasss 2015 Asset Title | Contract Code | Contract Description
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP01 | POST01-1 | Sign Post Type 1 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP01 | POST01-2 | Sign Post Type 1 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP01 | POST02-1 | Sign Post Type 2 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP01 | POST03-1 | Sign Post Type 3 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP02 | POST03-2 | Sign Post Type 3 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP02 | POST03-3 | Sign Post Type 3 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP02 | POST04-1 | Sign Post Type 4 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts
ST1.IDA.WG07.WT01.DES.001 - Supply of Parts | DESPLAP02 | POST04-2 | Sign Post Type 4 | AR | Ss_37_17_50_54 | Multi-function pole systems | LRS ST1SUP1 | Supplier of Parts