## Cover page
DMS-SD-140
Digital Engineering Guidance
Project Deliverables Requirements Guide
Version 3.0
Issued date: October 2019
Important Warning
This document is one set of standards developed solely and specifically for use on Transport Assets (as defined in the Asset Standards Authority Charter). It is not suitable for any other purpose. The copyright and any other intellectual property in this document will at all times remain the property of the State of New South Wales (Transport for NSW). You may not use or adapt this document or rely upon it in any way unless you are providing products or services to a NSW Government agency and that agency has expressly authorised you in writing to do so. If this document forms part of a contract with, or is a condition of approval by a NSW Government agency, use of the document is subject to the term of the contract or approval. To be clear, the content of this document is not licensed under any Creative Commons Licence. This document may contain third party material. The inclusion of third party material is for illustrative purposes only and does not represent an endorsement by NSW Government of any third party product or service. If you use this document or rely upon it without authorisation under these terms, the State of New South Wales (including Transport for NSW) and its personnel does not accept any liability to you or any other person for any loss, damage, costs and expenses that you or anyone else may suffer or incur from your use and reliance on the content contained in this document. Users should exercise their own skill and care in the use of the document. This document may not be current and is uncontrolled when printed or downloaded. Standards may be accessed from the Digital Engineering Framework website at:
www.transport.nsw.gov.au/digitalengineering

## Standard governance
DMS-SD-140
Project Deliverables Requirements Guide
Version 3.0
Issued date: October 2019
Standard governance
Owner: | Workstream Specialists
Authoriser: | Digital Engineering Program Manager
Approver: | Director Digital Engineering
Document history
Version | Summary of Changes
1.0 | For Information
2.0 | DE Framework documents Release 2.0
3.0 | DE Framework documents Release 3.0
For queries regarding this document,
please email the Digital Engineering team at
Digital.engineering@transport.nsw.gov.au
or visit www.transport.nsw.gov.au/digitalengineering

## Preface
DMS-SD-140
Project Deliverables Requirements Guide
Version 3.0
Issued date: October 2019
Preface
Transport for New South Wales (TfNSW) is developing the Digital Engineering (DE) Framework to enable time, cost and quality improvements to the way that projects are planned, designed, constructed, operated and maintained throughout their lifecycle. DE processes will provide TfNSW with an approach that enables digital information to become a key enabler of stakeholder engagement, decision making, improved asset knowledge, capability and capacity planning. Implementing and adhering to this vision will enable individuals, who are responsible for the delivery and management of TfNSW’s assets, to make more informed decisions. The DE Framework is yet to be delivered, and is currently in the early ‘Interim Approach’ stage of the program. This document should be read in conjunction with all related DE Framework Interim Approach documentation. Any application of the DE Framework Interim Approach or any of its parts must be considered in a project-specific context. Adoption of the DE Framework should be undertaken in consultation with the DE Team to ensure best appropriate practice.

## Project Deliverables Reqmts
Project Deliverables Requirements Guide
Table of guidance for DES minimum requirements, where the contract requires compliance with the DE Standard in its entirety. NOTE: This is a reference guide only. Project(s) may have departures from DE's qualifications to these requirements, of which must be included in the contract and agreed with TfNSW Project leads and DE manager. The contractor(s) should populate this table with their contracted scope.
Ref | DE Deliverables | TfNSW standards, templates and guides (DE Framework, ASA) | TfNSW project team schemas and templates | Contractor deliverables | Deliverable data details | Phased Contractor Requirements
[6 empty] | CMG0 | CMG1 | CMG2 |  |  | CMG3 |  | CMG4 | CMG5
[6 empty] | OPTIONS DESIGN | FEASIBILITY DESIGN | CONCEPT DESIGN | SYSTEMS DESIGN REVIEW (SDR) | PRELIMINARY DESIGN REVIEW (PDR) | CRITICAL DESIGN REVIEW (CDR) | APPROVED FOR CONSTRUCTION (AFC) | CONSTRUCTION | AS-BUILT | O&M
1 | DE Project Setup (Documents, Survey, Systems Engineering, CAD, BIM, GIS, Scheduling, Cost Estimating, Asset Data) | DMS-ST-202 Digital Engineering Standard Part 1: Concepts and Principles DMS-ST-207 Digital Engineering Standard Part 2: Requirements | - | - | - | - | - | - | - | - | - | - | - | -
|  | DMS-FT-548 Project Data Building Blocks (PDBB) Template | Project Data Building Blocks (not necessarily provided to Contractors - issue derived project data schemas instead) | - | - | - | - | - | - | - | - | - | - | -
|  | DMS-FT-533 Enterprise Content Management (ECM) Schema and Specification | Project ECM Schema and Specification | - | All deliverables to be submitted to the TfNSW ECM tool with compliant metadata | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
|  | DMS-FT-532 DE Framework Digital Engineering Execution Plan (DEXP) Template | Project or Contract DEXP Template | Contractor's DEXP | - | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
|  | DMS-FT-555 TfNSW Master Information Delivery Plan (MIDP) Template | Optional: Project MIDP template | Contractor's MIDP | Align metadata with Project Data Schemas (location, discipline, asset ID, ...) | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
2 | Survey | DMS-SD-142 Digital Survey Guide | Survey scope in contract documents | Digital survey | Align metadata with Project Data Schemas (location, discipline, asset ID, ...) | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
3 | CAD | DMS-FT-562 CAD Schema and Specification DMS-FT-549 DE Title Block DMS-FT-535 CAD Layer Naming Table DMS-SD-139 The DE CAD Concession | Project CAD Schema and Specification Optional: Project Title Block | Drawings for TfNSW project team | Requirements | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
[5 empty] | Drawing naming (per Project Milestones) | Options Design Drawing | Feasibility Design Drawing | Concept Design Drawing | Schematic Design Drawing | Preliminary Design Drawing | Detailed Design Drawing | AFC Drawing | Red-line mark-ups Drawing | WAE/As-Built Drawing
|  |  |  | Drawings for Virtual Plan Room (VPR) | To ASA T MU MD 00006 ST requirements | - | - | - | - | - | - | Required by ASA | Required by ASA | Required by ASA
|  | T MU MD 00006 F1 Metadata Spreadsheet for Engineering Drawings, v2.0 | - | Project Metadata Spreadsheet for Engineering Drawings |  | - | - | - | - | - | - | Required by ASA as part of CAD Concession for DE Framework | Required by ASA as part of CAD Concession for DE Framework | Required by ASA as part of CAD Concession for DE Framework
4 | BIM | DMS-FT-534 Model Production and Delivery Table (MPDT) Template | Optional: Project MPDT (blank or pre-populated) | Contractor MPDT | Requirements | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
|  | DMS-FT-532 DE Framework Digital Engineering Execution Plan (DEXP) Template | Project or Contract DEXP Template | Models for TfNSW project team (in alignment with Asset Register below) | Requirements | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | Formats (component models) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable) | Native + NWC (or project equivalent) + IFC (LandXML if applicable)
[5 empty] | Formats (federated models) | NWD (or project equivalent) | NWD (or project equivalent) | Native + NWD (or project equivalent) | NWD (or project equivalent) | Native + NWD (or project equivalent) | Native + NWD (or project equivalent) | Native + NWD (or project equivalent) | Native + NWD (or project equivalent) | Native + NWD (or project equivalent)
[5 empty] | Model Naming | Options Design Model | Feasibility Design Model | Concept Design Model | Schematic Design Model | Preliminary Design Model | Detailed Design Model | AFC Model | (If required by project) | AS-Built Model
[5 empty] | Level of Definition | 1 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5
[5 empty] | Level of Development | 100 | 100 | 200 | 200 | 200 | 300 | 300 | 300 | 400
|  | DMS-SD-133 BIM Schema and Specification DMS-SD-124 Application of Uniclass 2015 for Transport Guide (appropriate granularity of application) | Project BIM Schema and Specification |  | GUID | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | TfNSW Location ID | If required by project | If required by project | If required by project | If required by project | If required by project | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement
[5 empty] | TfNSW Parent Location ID | If required by project | If required by project | If required by project | If required by project | If required by project | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement
[5 empty] | TfNSW Asset ID | If required by project | If required by project | If required by project | If required by project | If required by project | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement
[5 empty] | TfNSW Parent Asset ID | If required by project | If required by project | If required by project | If required by project | If required by project | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement
[5 empty] | Project Asset ID | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
[5 empty] | Project Location Code | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Project Parent Location Code | If required by project | If required by project | Conditional DES requirement | If required by project | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | If design is updated | Conditional DES requirement
[5 empty] | Project Asset Code | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Project Parent Asset Code | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Asset Description | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Uniclass 2015 Asset Code | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Uniclass 2015 Location Code | If required by project | If required by project | Conditional DES requirement | If required by project | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | If design is updated | Conditional DES requirement
[5 empty] | Discipline Code | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Sub-discipline Code | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | If required by project | Conditional DES requirement | Conditional DES requirement | Conditional DES requirement | If design is updated | Conditional DES requirement
[5 empty] | Asset Status | If required by project | If required by project | If required by project | If required by project | If required by project | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Asset Owner | If required by project | If required by project | If required by project | If required by project | If required by project | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Asset Operator | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
[5 empty] | Asset Maintainer | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
[5 empty] | Start km | If required by project | If required by project | If required by project | If required by project | If required by project | Conditional DES requirement | Conditional DES requirement | If design is updated | Conditional DES requirement
[5 empty] | End km | If required by project | If required by project | If required by project | If required by project | If required by project | Conditional DES requirement | Conditional DES requirement | If design is updated | Conditional DES requirement
[5 empty] | GPS Coordinates | If required by project | If required by project | If required by project | If required by project | If required by project | Conditional DES requirement | Conditional DES requirement | If design is updated | Conditional DES requirement
[5 empty] | Design Work Package Code | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
[5 empty] | Construction Work Package Code | If required by project | If required by project | Required by DES if known | If required by project | Required by DES if known | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | Commissioning Work Package Code | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
[5 empty] | General model property: Project Name | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | General model property: Project Contract Code | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | General model property: AEO company code | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | General model property: AEO company name | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | General model property: Design company code | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | General model property: Design company name | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | General model property: Co-ordinate system | Required by DES | Required by DES | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
|  | DMS-FT-556 Model Validation Certificate Template | - | Model Validation Certificate | Requirements | If required by project | If required by project | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
|  | DMS-ST-207 Digital Engineering Standard Part 2: Requirements | - | Models for Virtual Plan Room (VPR) | Requirements | - | - | - | - | - | - | Individual + Federated model(s) | Individual + Federated model(s) | Individual + Federated model(s)
[5 empty] | Formats | - | - | - | - | - | - | Native (zip) + NWD/NWC + IFC | Native (zip) + NWD/NWC + IFC | Native (zip) + NWD/NWC + IFC
5 | GIS | GIS Guide (pending next release) | - | GIS datasets | Align metadata with Project Data Schemas (location, discipline, asset ID, ...) | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
6 | Scheduling | DMS-FT-520 Scheduling Schema and Specification | Work Breakdown Structure (WBS) | Contractor schedule | Align metadata with Project Data Schemas (location, discipline, asset ID, ...) | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
7 | Cost Estimating | DMS-FT-520 Scheduling Schema and Specification | Cost Breakdown Structure (CBS) | Contractor earned value analysis plus cost deliverables as defined by scope | Align metadata with Project Data Schemas (location, discipline, asset ID, ...) | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
8 | Asset Data | DMS-FT-537 Asset Register Template | Project Asset Register Template | Project/Contractor Asset Register | Requirements | - | - | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | Required by DES | Required by DES
[5 empty] | Asset Register Name | - | - | Concept Design Asset Register | Systems Design Asset Register | Preliminary Design Asset Register | Detailed Design Asset Register | AFC Asset Register | If required by project | Handover As-Built Asset Register
|  |  |  | Project/Contractor Asset Register (Asset List worksheet) | Uniclass 2015 Asset Code (Ss, or EF, or Pr) | - | - | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Ss - minimum granularity for systems | - | Ss_xx | Ss_xx_xx | Ss_xx_xx | Ss_xx_xx | Ss_xx_xx_xx | Ss_xx_xx_xx_xx | Ss_xx_xx_xx_xx | Ss_xx_xx_xx_xx
[5 empty] | EF - minimum granularity for elements | - | EF_xx | EF_xx | EF_xx | EF_xx | EF_xx_xx | EF_xx_xx | EF_xx_xx | EF_xx_xx
[5 empty] | Pr - minimum granularity for products | - | - | Pr_xx_xx | Pr_xx_xx | Pr_xx_xx | Pr_xx_xx_xx | Pr_xx_xx_xx | Pr_xx_xx_xx | Pr_xx_xx_xx
[5 empty] | Other attributes as required by DE Standard and found in the Asset Register Template: project asset code, project parent asset code, asset description, project location code, discipline code, sub-discipline code, work package (design, construction, commissioning), start km, end km, GPS coordinates, asset status, asset owner, asset operator, asset maintainer, maintenance managed item, modelled asset, source model, model object guid. | - | - | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Uniclass 2015 Location Code (Co, or EN, or SL) | - | - | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
[5 empty] | Co - minimum granularity for complexes | Co_xx | Co_xx | Co_xx_xx | Co_xx_xx | Co_xx_xx | Co_xx_xx_xx | Co_xx_xx_xx | Co_xx_xx_xx | Co_xx_xx_xx
[5 empty] | En - minimum granularity for entities | - | En_xx | En_xx | En_xx | En_xx | En_xx_xx_xx | En_xx_xx_xx | En_xx_xx_xx | En_xx_xx_xx
[5 empty] | SL - minimum granularity for spaces/locations | - | SL_xx | SL_xx_xx | SL_xx_xx | SL_xx_xx | SL_xx_xx_xx | SL_xx_xx_xx | SL_xx_xx_xx | SL_xx_xx_xx
[5 empty] | Other attributes as required by DE Standard and found in the Asset Register Template: project location code, project parent location code, project location description, corridor, state, suburb, ASA location, GPS coordinates, start km, end km. | - | - | Required by DES | If required by project | Required by DES | Required by DES | Required by DES | If design is updated | Required by DES
8 | Systems Assurance | DMS-FT-563 Requirements Schema for DE | - | - | Align metadata with Project Data Schemas (location, discipline, asset ID, ...) | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project
9 | Visualisation | DMS-SD-130 Visualisation Requirements Guide | - | As defined in project scope, including visualisation deliverable, production files and content used in the development of the visualisation. Specfic executable (.exe) files to run/view visualisation. | Deliverable medium properties inluding frame rate, resolution, DPI, codec. | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project | If required by project