## Sheet1
Work Plan - Implementing works
Program Name: |  | Boating Access Dredging Program (2021)
Grant Recipient:
Project Name:
Grant Reference No (MIDO to complete):
Grant funding sought: |  |  | Total Project Cost:
Expected Funding Term Completion Date: |  |  | Funding Level/Ratio:
Project Manager: |  |  | Phone: |  | Date Prepared:
Milestone Number | Milestone | Activities | Outputs | Projected Milestone Completion Date (dd/mm/yyyy) | Total Estimated Milestone Cost (all contributions) GST exclusive | Estimated Milestone Payment Amount (Government contribution only) GST exclusive
1 | Design and optimisation of channel position and configuration | Examples of potential activities include: - Identify/optimise potential dredge options to maximise navigation and/or tidal exchange. - Assess influence of key estuarine and coastal processes on waterway conditions and longevity of dredge options. | Examples of potential outputs include: - Incorporate key aspects of report in the environmental review and relevant documentation.
2 | Environmental review of proposed works and approvals | Examples of potential activities include: - Seek and take into account the requirements of relevant authorities. - Finalise detailed project plan and specifications. - Undertake all necessary studies. - Prepare draft environmental assessment and obtain all relevant approvals. - Finalise environmental assessment. prepare final work plans and specifications. | Examples of potential outputs include: - Planning approval and all other relevant approvals obtained. - Final work plans and specifications approved for tender documentation.
3 | Engage contractor* | Examples of potential activities include: - Finalise proposed works and submit detailed work plan. - Prepare tender documents. - Call for tenders. - Tender process and approval. - Award contract. | Examples of potential outputs include: - Contractor engaged.
4 | Undertake dredging and beach nourishment activities | Examples of potential activities include: - Dredge mobilisation and demobilisation. - Dredge (quantity) of material to placement location. - Pre and post dredge surveys. | Examples of potential outputs include: - (quantity) of material delivered to placement location. - dredge surveys completed. (payment schedule to be identified)
5 | Post project monitoring (if required)
| Final Report |  | Grant acquitted |  | N/A
| Totals |  |  |  | 0 | 0
*This milestone not needed if approval has been given to undertake in-house.
Submit preliminary Work Plan with Funding Application.
For the use of the Maritime Infrastructure Delivery Office - Transport for NSW
I have reviewed this Work Plan and approve / do not approve it (delete whichever is not applicable)
Name |  | Date | Signature/Email approval
EXAMPLE ONLY