## G.4 Quarterly KPM Report (M2)
G.4 QUARTERLY KPM REPORT
QUARTERLY KPM REPORT
KPM No. | KPM | Threshold |  | Current result | Comparison with previous result | Comment
|  | AMBER | RED
ROUTINE SERVICES KPMs
RQ1 | Forecasting accuracy – Percentage by which actual expenditure on Routine Services varies from agreed forecast. | > ±10% | > ±20% | -6% | ê
RQ2 | Defect management – Percentage of one kilometre segments that are non-compliant in regard to Mandatory Activities. | > 10% | > 20% | 4% | é
ORDERED WORK KPMs | Ordered Work KPMs
OQ1 | Value for money – Percentage that payment for Ordered Works (valued at more than $100,000) exceeds the summation of Benchmark Prices. | > 5% | > 15% | 7% | ê
OQ2 | Project delivery – Percentage of projects that achieve completion date stated in the Work Order. | < 85% | < 70% | 92% | ê
OQ3 | Quality of work - Percentage of rework for heavy patching, spray sealing, asphalt resurfacing and pavement rebuilding. | > 2% | > 5% | 1% | é
MANAGEMENT KPMs | Management KPMs
MQ1 | Inspections - Percentage of scheduled inspections not completed in quarter. | > 5% | > 10% | 8% | é
MQ2 | Reporting - Submission of complete and accurate quarterly Progress Report including the KPM report, accomplishment report and current RMAP. | More than 2 weeks late | More than 1 month late | On time | ó
MQ3 | Quality System – Number of NCRs not closed out plus the number of NPSNs issued in the quarter. | > 2 | > 5 | 1 | é
MQ4 | Customer service – Percentage of enquiries or complaints within quarter that are unresolved for more than 4 weeks. | >5% | >10% | 4% | é