## Cover page
DMS-FT-555
Digital Engineering Template
Master Information Delivery Plan (MIDP) Template
Version: | 4.4
Issued date: December 2022
Important Warning
This document is one set of standards developed solely and specifically for use on Transport Assets (as defined in the Asset Standards Authority Charter). It is not suitable for any other purpose. The copyright and any other intellectual property in this document will at all times remain the property of the State of New South Wales (Transport for NSW). You may not use or adapt this document or rely upon it in any way unless you are providing products or services to a NSW Government agency and that agency has expressly authorised you in writing to do so. If this document forms part of a contract with, or is a condition of approval by a NSW Government agency, use of the document is subject to the term of the contract or approval. To be clear, the content of this document is not licensed under any Creative Commons Licence. This document may contain third party material. The inclusion of third party material is for illustrative purposes only and does not represent an endorsement by NSW Government of any third party product or service. If you use this document or rely upon it without authorisation under these terms, the State of New South Wales (including Transport for NSW) and its personnel does not accept any liability to you or any other person for any loss, damage, costs and expenses that you or anyone else may suffer or incur from your use and reliance on the content contained in this document. Users should exercise their own skill and care in the use of the document. This document may not be current and is uncontrolled when printed or downloaded. Standards may be accessed from the Digital Engineering Framework website at:
www.transport.nsw.gov.au/digitalengineering

## Preface
DMS-FT-555
Master Information Delivery Plan (MIDP) Template
Version:4.4
Issued date: December 2022
Preface
Transport for New South Wales (TfNSW) is developing and implementing the Digital Engineering (DE) Framework to support projects as they adopt new digital ways of working. The way assets are planned, designed, constructed, operated and maintained are becoming faster and more accurate as a result of emerging technologies. The DE Framework connects these technologies across various project disciplines together with reliable, structured data. Consistent DE processes provide TfNSW with an approach that enables digital information to become a key enabler of better project outcomes. This includes, but is not limited to; stakeholder engagement, informed decision making, improved asset knowledge, capability and capacity planning. Applying this unified vision will accelerate the value of DE, and simplify these new ways of working for both our project teams and industry, providing valuable insights, creating efficiencies and delivering cost savings throughout the project lifecycle. This document should be read in conjunction with all related DE Framework documentation. Any application of the DE Framework or any of its parts must be considered in a project-specific context. Adoption of the DE Framework should be undertaken in consultation with the DE Team to ensure best appropriate practice.

## Standard governance
DMS-FT-555
Master Information Delivery Plan (MIDP) Template
Version:4.4
Issued date: December 2022
Standard governance
Owner: | Workstream Specialists
Authoriser: | Senior Manager Digital Engineering Governance
Approver: | Director Digital Twin Integration
Document history
Version | Summary of Changes
1.0 | For Information - Draft Only
2.0 | For Release 2
3.0 | For Release 3
4.0 | For Release 4. Template updated to allow ECM PDS data integration.
4.2 | For Release 4.2. Improved data validation with ECM PDS
4.3 | For Release 4.3 onwards. Update on data validation with ECM PDS
4.4 | For DE Standard Release 4.1 Update "Document Governance" and rename to "Project Document Governance" Update of ECM PDS to align with DE Standard Release 4.1
For queries regarding this document,
please email the Digital Engineering team at
Digital.engineering@transport.nsw.gov.au
or visit www.transport.nsw.gov.au/digitalengineering

## MIDP Template
Master Information Delivery Plan (MIDP)
PROJECT ALIAS:
PROJECT NAME: | My Project
DOCUMENT NUMBER: |  |  |  | *This template is to be used in conjunction with the Digital Engineering Execution Plan (DEXP) | [25 empty] | MILESTONE 01 |  |  | MILESTONE 02 |  |  | MILESTONE 03 |  |  | MILESTONE 04 |  |  | MILESTONE 05 |  |  | MILESTONE 06
DOCUMENT OWNER: |  |  |  | REFER TO ECM SCHEMA FOR CODES | [11 empty] | CURRENT REVISION | CURRENT VERSION | EXCHANGE FORMATS |  |  |  |  | WORK ZONE |  |  | WORK PACKAGE |  | SUBMISSION NOTES |  | MILESTONE NAME: | Management |  | MILESTONE NAME: | Management |  | MILESTONE NAME: | Management |  | MILESTONE NAME: | Management |  | MILESTONE NAME: | Procurement (TfNSW) |  | MILESTONE NAME: | Procurement (TfNSW)
DATE CREATED: |  |  |  | DOCUMENT NUMBER | [25 empty] | STAGE: | Initiation - Needs Confirmation (IAG Gate 0) |  | STAGE: | Planning and Development - Needs Analysis (IAG Gate 1) |  | STAGE: | Initiation - Needs Confirmation (IAG Gate 0) |  | STAGE: | Planning and Development - Needs Analysis (IAG Gate 1) |  | STAGE: | Initiation - Needs Confirmation (IAG Gate 0) |  | STAGE: | Planning and Development - Investment Decision (IAG Gate 2)
DATE LAST UPDATED: | [15 empty] | As per document | As per document | As per contract |  |  |  |  | Agree work zones with client |  |  | Agree packages with client |  | Agree with client |  | PROGRAMME REF: |  |  | PROGRAMME REF: |  |  | PROGRAMME REF: |  |  | PROGRAMME REF: |  |  | PROGRAMME REF: |  |  | PROGRAMME REF:
DELIVERABLE (DOCUMENT TITLE) | DOCUMENT DESCRIPTION | STATE | SUITABILITY STATUS | PROJECT CONTRACT NAME | PROJECT CONTRACT CODE | ORIGINATOR | ORIGINATOR CODE | LOCATION DESCRIPTION | LOCATION CODE | SUB-LOCATION DESCRIPTION | SUB-LOCATION CODE | DISCIPLINE DESCRIPTION | DISCIPLINE CODE | SUB-DISCIPLINE DESCRIPTION | SUB-DISCIPLINE CODE | DOCUMENT TYPE NAME | DOCUMENT TYPE CODE | NUMBER | FULL DOC NUMBER (CONCATENATION) | REVISION NO | VERSION NO (CONTRACTOR USE ONLY) | FILE EXTENSION (comma separated e.g. PDF, DWG) | WORK ZONE GROUP NAME | WORK ZONE NAME | WORK ZONE CODE | WORK PACKAGE GROUP | WORK PACKAGE NAME | WORK PACKAGE CODE | FREQUENCY / MILESTONES / SECURITY NOTES / COMMENTS | RESPONSIBLE PARTY (MILESTONE 1) | ISSUE DATE (MILESTONE 1) | TRANSMITTAL NUMBER (MILESTONE 1) | RESPONSIBLE PARTY (MILESTONE 2) | ISSUE DATE (MILESTONE 2) | TRANSMITTAL NUMBER (MILESTONE 2) | RESPONSIBLE PARTY (MILESTONE 3) | ISSUE DATE (MILESTONE 3) | TRANSMITTAL NUMBER (MILESTONE 3) | RESPONSIBLE PARTY (MILESTONE 4) | ISSUE DATE (MILESTONE 4) | TRANSMITTAL NUMBER (MILESTONE 4) | RESPONSIBLE PARTY (MILESTONE 5) | ISSUE DATE (MILESTONE 5) | TRANSMITTAL NUMBER (MILESTONE 5) | RESPONSIBLE PARTY (MILESTONE 6) | ISSUE DATE (MILESTONE 6) | TRANSMITTAL NUMBER (MILESTONE 6)
|  | WORK IN PROGRESS | NOT FOR SHARING | Design Contract ABC |  | A W Edwards Pty Limited |  | Level 1 |  | Level 2 |  | Architectural | AR | Architectural Signage System | AS | Agreement | AGR | 1 | ---AS-AGR-000001 |  |  |  | Castelreagh Highway |  |  | WG01 - Design
|  |  |  | Design Tunnel |  | Transport for NSW |  | Castlereagh Highway |  |  |  | Civil | CV | Stormwater Drainage | SD | Bill of Quantities | BOQ | 1 | ---SD-BOQ-000001 | [6 empty] | WG02 - Supply
-----000000
-----000000
-----000000
-----000000
-----000000
-----000000
-----000000
-----000000
-----000000
-----000000
-----000000
-----000000

## Using this template
Using this MIDP template
This template has been updated to allow integration with the ECM Project Data Schema (PDS)
The ECM PDS is a controlled project document which is managed using the DMS-FT-548 Project Data Building Blocks (PDBB) Template.
Where projects determine it is beneficial, the Project ECM PDS may be updated via the PDBB and changes to the ECM PDS can be automatically published into this MIDP Template.
This workflow has the following benefits:
1. The ECM and MIDP meta-data is aligned
2. The data validation (i.e. drop down fields) built into this MIDP template are refreshed to align with the ECM meta-data
3. Automatic document numbering in this MIDP template is aligned.
Note, manually replacing the ECM PDS worksheet will result in the loss of the data validation.
Please contact your TfNSW DE Manager for assistance with updating of this template.

## Project Document Governance
Project Number:
Project Title:
Document Number: | DMS-FT-555-
Document Title:
TfNSW DE Template Release Version: | 4.4
Document Governance
Owner: | Digital Engineering Manager
Endorser: | Document Controller Manager/Senior Document Controller/Document Controller
Approver:
Document History
Revision History | Summary of Changes | Date Created/ Updated

## ECM PDS
ECM PDS |  | DE Standard | 4.1 | PDBB Version |  | Date Updated
| ECM METADATA SCHEMA |  |  | PROJECT CONTRACT CODE | [7 empty] | ORIGINATOR |  | TFNSW STAGE/ PROJECT MILESTONE |  |  |  | LOCATION | [12 empty] | Work Zone | [13 empty] | DISCIPLINE | [8 empty] | DOCUMENT TYPE |  |  | SHEET NUMBER | PROJECT REVISION NUMBERS |  |  | OWNER |  |  |  |  | COMMON DATA ENVIRONMENT STATE AND SUITABILITY | [10 empty] | OTHER | [10 empty] | Work Zone
| InEight Doc UI: Document No. | InEight Doc UI: Title |  | HIDDEN in InEight Doc UI |  | InEight Doc UI: Sub-Project |  | InEight Doc UI: Contract |  |  |  | InEight Doc UI: Originator |  | CURRENT NOT AVAILABLE in InEight Doc UI |  | InEight Doc UI: Project Milestone |  | InEight Doc UI: Location |  |  | InEight Doc UI: Sub-Location |  |  | InEight Doc UI: Sub-Sub Location |  |  |  |  | InEight Doc UI: Area |  | InEight Doc UI: Work Zone |  |  |  | InEight Doc UI: Sub-Work Zone |  |  |  | InEight Doc UI: Sub-Sub Work Zone | [5 empty] | InEight Doc UI: Discipline |  |  |  |  | InEight Doc UI: Sub-Discipline |  |  |  | InEight Doc UI: Type |  |  | InEight Doc UI: Serial Number | InEight Doc UI: Rev | InEight Doc UI: Version | InEight Doc UI: Revision Notes | CURRENT NOT AVAILABLE in InEight Doc UI |  | InEight Doc UI: ASA VPR Discipline | InEight Doc UI: ASA EDMS ID | InEight Doc UI: ASA Amendment No | InEight Doc UI: State |  | InEight Doc UI: Status |  |  | InEight Doc UI: Review Status | [5 empty] | InEight Doc UI: Work Package |  |  |  |  | InEight Doc UI: Security Classification |  | InEight Doc UI: BIM Reference | InEight Doc UI: GIS Reference | InEight Doc UI: Contractor Doc No | InEight Doc UI: Remarks
| Document No* | Title* |  | Program* |  | Project |  | Contract* |  |  |  | Originator* |  | INSW Phase/TfNSW Stage |  | Project Milestone (I&P)* |  | Location* |  |  | Sub-Location |  |  | Sub-sub-Location |  |  |  |  | Area |  | Work Zone (L1) |  |  |  | Sub-Work Zone (L2) |  |  |  | Sub-sub-Work Zone (L3) | [5 empty] | Discipline* |  |  |  |  | Sub-Discipline |  |  |  | Document Type* |  |  | Serial Number | Revision* | TfNSW Version | Amendment Description | Required for Handover | Asset Owner | ASA VPR Discipline | ASA EDMS ID | ASA Amendment No | State* |  | Suitability* |  |  | Review Status |  |  | Work Package Group |  |  | Work Package |  |  |  |  | Security Classification |  | BIM Reference | GIS Reference | Contractor Doc No | Remarks | Work Zone Information
| Up to 40 characters including hyphens. In InEight Document: input "AUTO" for auto document number sequencing OR: Manual user input. | Text field - Up to 40 characters Mandatory user Input. Manual text entry. |  | Mandatory and fixed to one value only. Up to 4 characters Auto (no user input) |  | Project to decide whether to use this field. Only required for Program's using one combined ECM for multiple projects. Mandatory when UnHidden Up to 6 characters Must be uniform length Auto (no user input) |  | Concatenation of Program with Project. It helps to identify project with asscoiated program | Contract name are defined as part of the commercial strategy process when the Client determines how a project will be delivered. Contract Alias is code for the contract name. Contract Alias is defined by project. |  | Maximum 10 characters - recommend fewer. Project Contract code is included in the document number. Project Contract Code would be a concatantion of Program+ Project+ Contract Alias | Align with the T MU AM 01007 TI Asset Reference Codes Register Request new Orginator code from Digital Engineering Team. Company / contract Up to 5 characters Mandatory user selection with drop-down pick-list, defaults to the user's company code. |  | Align with the first tier of INSW Infrastructure Investor Assurance Framework. Optional TBD by Project director Not concatenated in document number. Dropdown list aligned with INSW Phases and TfNSW Investment Stages. Mandatory when unhidden, user selection with suggestion list. |  | Align with the first tier of INSW Infrastructure investor Assurance Framework, Department of planning, industry and envioronmental (DPIE), Property of NSW Assurance and TfNSW configuration management plan in accordance with T MU AM 04001 PL. Not included in document number. Upto 32 character limit for Project Milestone Description Mandatory user selection with drop-down pick-list. |  | Align with the first tier of ASA locations where applicable using the corridor or location/site tabs in T MU AM 01007 TI, in accordance with T MU AM 01006 ST. Request new ASA location codes using T MU AM 01006 F1. 3 character limit for rail projects Mandatory user selection from drop-down pick-list. Project-defined default. This code is incorporated into the concatenated document number if Sub-Location is not defined. |  |  | Sub-Location is a child of Location. All Sub-Location codes must include their parent Location Code, in order to ensure uniqueness when using ASA locations or similar. Align with ASA locations where applicable, or define project-specific hierarchy if ASA do not need to define the codes. A combination of ASA and non-ASA codes may co-exist but should be highlighted. 6 character limit. Optional user selection with drop-down pick-list dependent on the selected Location code. No default. A generic code 'ALL' is not required - simply do not select this field. This code is incorporated into the document number if used |  |  | Sub-Sub-Location is a child of Sub-Location. All Sub-Sub-Location codes must include their parent Sub-Location Code, in order to ensure uniqueness when using ASA locations or similar. Align with ASA locations where applicable, or define project-specific hierarchy if ASA do not need to define the codes. A combination of ASA and non-ASA codes may co-exist but should be highlighted. 10 character limit. Optional user selection with drop-down pick-list dependent on the selected Location code. No default. A generic code 'ALL' is not required - simply do not select this field. This code is incorporated into the document number if used. |  |  |  |  | Optional user selection with drop-down pick-list dependent on the selected Location code. No default. A generic code 'ALL' is not required - simply do not select this field. This code is not incorporated into the document number. |  | Work Zone are pyhsical, geo-spatial locations defined by projects during delivery. Work Zones can be organized into Work Zone groups. |  |  | Contractor responsible to execute work in the specified work Zone. | Child of Work Zone (L1) |  |  |  | Child of Work Zone (L2) | [6 empty] | Parent of Sub-Discipline. 2 characters. Mandatory user selection with drop-down pick-list. This field is incorporated into the concatenated document number if Sub-Discipline is not selected. |  |  |  |  | Child of Discipline. 2 characters. Optional user selection with drop-down pick-list dependent on selected Discipline. This field is incorported into the concatenated document number if it is selected. |  |  | 3 characters. Mandatory user selection with drop-down pick-list. No default value. This field is incorporated into the concatenated document number. |  |  | 6 digits Optional user input. Defaults to next available number if left blank. Before user can progress with a document upload, automatic validation must confirm that the total concatenated doc number is unique. | Manual or automatic. Increased each time an artefact is loaded at shared state. A to ZZ (before AFC) 00-99 (for Construction) Mandatory user selection with default suggestion list. | This field is automated by TeamBinder. This version number is not equal to the Contractor's internal version number (which appears on drawing title blocks). Each new instance of a file increments. Drops to zero upon new revision number. | Optional Manual user input. Use this field to indicate Contractor's internal version number if appropriate. | Is this information required for handover to the asset owner for operation, maintenance and/or other aspects of the full asset lifecycle? | The organisation which will be the owner of this information after handover. | Align with the first tier of ASA Engineering Drawings and CAD Requirements where applicable in accordance with T MU AM 00006 ST. Optional, as required at configuration gates. 2 characters Default suggestion list with no addition required | Align with the first tier of ASA Engineering Drawings and CAD Requirements where applicable in accordance with T MU AM 00006 ST. Numbers to be agreed with ASA prior to submission into the Virtual Plan Tool. 7 digits Manual user input | Align with the first tier of ASA Engineering Drawings and CAD Requirements where applicable in accordance with T MU AM 00006 ST. Optional, as required at configuration gates. 2 characters Default suggestion list Manual user input | Align with the first tier of ISO 19650 & PAS 1192:2007 + A2:2016 where applicable using the Common data environment (CDE) concept. Mandatory user selection with drop-down pick-list. |  | Align with the first tier of ISO 19650 & PAS 1192:2007 + A2:2016 where applicable using the Common data environment (CDE) concept and in accordance with TfNSW Design & Construct Works Brief. Mandatory user selection with drop-down pick-list. |  |  | Align with the first tier of ISO 19650 & PAS 1192:2007 + A2:2016 where applicable using the Common data environment (CDE) concept and in accordance with TfNSW Design & Construct Works Contract. Driven by the review workflow engine in InEight Document. Codes to be agreed by the project document controller. |  |  | Classification of work package agreed by project Work packages includes Design, Construction, Commissioning, Supply and Management |  |  | Dropdown picklist. To include list of all work packages including Design, Construction, Commissioning and Supply and Management. TBD by TfNSW Project lead. Up to 10 characters for Work Package Code Up to 50 characters for Description for Work Package name description |  |  |  | Multiple Work Package could be assigned to a single project contract if the program has more than one project contract. | Up to 50 characters. According to 'NSW Government Information Classification, Labelling and Handling Guidelines' User selection, defaults to UNCLASSIFIED. All DLM Labelling TBD by the Project. |  | Optional field for hyperlinks or model references | Optional field for hyperlinks or model references | Optional. Alternative Contractor Doc Number Manual user input | Optional
Sequence | 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 |  |  |  | 22 | 23 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 |  |  |  | 33 | 34 | 35 |  | 36 | 37 | 38 |  |  | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 |  |  | 50 | 51 | 52 | 53 | 54 | 55 | 56 |  | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80
TfNSW Field Name | Document Number | Document Title |  | Program Alias | Program Name | Program Project Alias | Project Name | Parent Program Project Alias | Contract Alias | Contract Name | Project Contract Code | Contracted Organisation Code | Contracted Organisation Name | Phase Stage Code | Phase Stage Description | Project Milestone Code | Project Milestone Description | Asset Location Code (L1) | Asset Location Description (L1) | Asset Location Remarks | Asset Location Code (L2) | Asset Location Description (L2) |  |  |  | Asset Location Code (L3) | Asset Location Description (L3) |  | n/a | n/a | Work Zone Group Name | Work Zone Code (L1) | Work Zone Name (L1) | Work Zone Owner | Work Zone Code (L2) | Work Zone Name (L2) | Work Zone Owner |  |  |  | Work Zone Code (L3) | Work Zone Name (L3) | Work Zone Owner |  | Discipline Category | Discipline Code | Discipline Description |  |  | Discipline Category | Discipline Code | Sub-discipline Code | Sub-discipline Description | Document Type Code | Document Type Name | Document Type Use | Serial Number | Document Revision Number | Document Version Number | Amendment Description |  |  | ASA VPR Discipline Code | ASA EDMS ID | ASA Amendment Number | State Code | State Description | Suitability Code | Suitability Description |  | Review Outcome Code | Review Outcome Description | Review Outcome Remarks | Work Package Group | Work Package Group Name | Work Package Group | Work Package Group | Work Package Group | Work Package Code | Work Package Name | Project Contract Code | Security Classification Code | Security Classification Description | BIM Reference Link | GIS Reference Link | Contractor Document Number | ECM Remarks | Worl Zone Group Name | Work Zone Group Code | Work Zone Group Name | Work Zone Code | Work Zone Name | Work Zone Display | Work Zone Owner
TfNSW Attribute Name | TfNSW_DocumentNo | TfNSW_DocumentTitle |  | TfNSW_ProgramAlias | TfNSW_ProgramName | TfNSW_ProgramProjectAlias | TfNSW_ProjectName | TfNSW_ParentProgramProjectAlias | TfNSW_ContractAlias | TfNSW_ContractName | TfNSW_ProjectContractCode | TfNSW_ContractOrgCode | TfNSW_ContractOrgName | TfNSW_PhaseStageCode | TfNSW_PhaseStageDesc | TfNSW_ProjectMilestoneCode | TfNSW_ProjectMilestoneDesc | TfNSW_AssetLocationCodeL1 | TfNSW_AssetLocationDescL1 | TfNSW_AssetLocationRemarks | TfNSW_AssetLocationCodeL2 | TfNSW_AssetLocationDescL2 |  |  |  | TfNSW_AssetLocationCodeL3 | TfNSW_AssetLocationDescL3 |  | n/a | n/a | TfNSW_WorkZoneGroupName | TfNSW_WorkZoneCodeL1 | TfNSW_WorkZoneNameL1 | TfNSW_WorkZoneOwner | TfNSW_WorkZoneCodeL2 | TfNSW_WorkZoneNameL2 | TfNSW_WorkZoneOwner |  |  |  | TfNSW_WorkZoneCodeL3 | TfNSW_WorkZoneNameL3 | TfNSW_WorkZoneOwner |  | TfNSW_DisciplineCategory | TfNSW_DisciplineCode | TfNSW_DisciplineDesc |  |  | TfNSW_DisciplineCategory | TfNSW_DisciplineCode | TfNSW_SubDisciplineCode | TfNSW_SubDisciplineDesc | TfNSW_DocumentTypeCode | TfNSW_DocumentTypeName | n/a | TfNSW_SerialNumber | TfNSW_DocumentRevisionNo | TfNSW_DocumentVersionNo | TfNSW_AmendmentDesc |  |  | TfNSW_ASAVPRDisciplineCode | TfNSW_ASAEDMSID | TfNSW_AmendmentNo | TfNSW_StateCode | TfNSW_StateDesc | TfNSW_SuitabilityCode | TfNSW_SuitabilityDesc |  | TfNSW_ReviewOutcomeCode | TfNSW_ReviewOutcomeDesc | TfNSW_ReviewOutcomeRemarks | TfNSW_WPGroupID | TfNSW_WPGroupName | TfNSW_WPGroup | TfNW_WPGroupID | TfNSW_WPGroup | TfNSW_WPCode | TfNSW_WPName | TfNSW_ProjectContractCode | TfNSW_SecurityClassificationCode | TfNSW_SecurityClassificationDesc | TfNSW_BIMReferenceLink | TfNSW_GISReferenceLink | TfNSW_ContractorDocNo | TfNSW_ECMRemarks | TfNSW_WorkZoneGroupName | TfNSW_WorkZoneGroupCode | TfNSW_WorkZoneGroupName | TfNSW_WorkZoneCode | TfNSW_WorkZoneName | #N/A | TfNSW_WorkZoneOwner
ECM Field Name | Document Number | Document Title |  | Program Alias | Program Name | Program Project Alias | Project Name | Parent Program Project Alias | Contract Alias | Contract Name | Project Contract Code | Contracted Organisation Code | Contracted Organisation Name | Phase Stage Code | Phase Stage Description | Project Milestone Code | Project Milestone Description | Asset Location Code (L1) | Asset Location Description (L1) | Asset Location Remarks | Asset Location Code (L2) | Asset Location Description (L2) | Parent Asset Location Code | Parent Sub-Location (parts 1 and 2) | Third and further tiers in location hierarchy (part 3) | Asset Location Code (L3) | Asset Location Description (L3) | Parent Asset Location Code | Area Code | Area Description | Work Zone Group Name | Work Zone Code (L1) | Work Zone Name (L1) | Work Zone Owner | Work Zone Code (L2) | Work Zone Name (L2) | Work Zone Owner | Parent Work Zone Code | Parent Sub-Location (parts 1 and 2) | Third and further tiers in location hierarchy (part 3) | Work Zone Code (L3) | Work Zone Name (L3) | Work Zone Owner | Parent Work Zone Code | Discipline Category | Discipline Code | Discipline Description | ASA Discipline Code (P&I_ RevA) | ASA Discipline Description | Discipline Category | Discipline Code | Sub-Discipline Code | Sub-Discipline Description | Document Type Code | Document Type Name | Document Type Use | Serial Number | Document Revision Number | Document Version Number | Amendment Description | Attribute | Attribute | ASA VPR Discipline Code | ASA EDMS ID | Attribute | State Code | State Description | Suitability Code | Suitability Description | Remarks | Review Outcome Code | Review Outcome Description | Remarks | Work Package Group ID | Work Package Group Name | Work Package Group | Work Package Group ID | Work Package Group | Work Package Code | Work Package Name | Project Contract Code | Security Classification Code | Security Classification Description | BIM Reference Link | GIS Reference Link | Contractor Doc No | ECM Remarks | Work Zone Group Name | Work Zone Group Code | Work Zone Group Name | Work Zone Code | Work Zone Name | Work Zone Display | Work Zone Owner
| [Project Contract Code]- | [12 empty] | IDA | Initiation - Needs Confirmation (IAG Gate 0) | M010 | Management | NWW | Network Project Wide | Default location as per AMB code (NWW) |  |  |  | #REF! | 01 | [13 empty] | #REF! | 01 |  |  |  |  | Technical | AR | Architectural |  |  | Technical | AR | AS | Architectural Signage System | AGR | Agreement | Including Third parties agreements |  |  |  |  | Yes | ASA | CV |  | A….(For AFC) | A | WORK IN PROGRESS | S0 | NOT FOR SHARING |  | REL-COM | Released subject to comments and to resubmit document |  | WG01 | Design | WG01 - Design | [5 empty] | UNOFF | UNOFFICIAL
| [Originator Code]- | [12 empty] | INI | Planning and Development - Needs Analysis (IAG Gate 1) | M020 | Procurement (TfNSW) | [6 empty] | #REF! | 01001 | [13 empty] | #REF! | 01001 |  |  |  |  | Business | CI | Cyber Security | AR | Architecture & services | Technical | AR | AT | Architecture Design | ANA | Analysis | Financial risk model, Failure Mode, Effects & Criticality Analysis (FMECA) |  |  |  |  | No |  | EL |  | B….(Re-issued for Construction) | B | SHARED | S1 | FOR COORDINATION |  | RELEASED | Released (released for information only - no review required) |  | WG02 | Supply | WG02 - Supply | [5 empty] | OFF | OFFICIAL
| [Location or Sub-Location]- | [12 empty] | PLD | Planning and Development - Investment Decision (IAG Gate 2) | M030 | Planning Approval | [6 empty] | #REF! | 01 | [13 empty] | #REF! | 01 |  |  |  |  | Business | CM | Commercial Management | TE | Technology & telecommunications | Technical | AR | DU | Urban Design | APL | Approval | [7 empty] | FL |  | C….(As built) | C | CLIENT SHARED | S2 | FOR INFORMATION |  | REV-RES | Revise and resubmit (Document not fit for review) |  | WG03 | Construction | WG03 - Construction | [5 empty] | OFF-SEN-CAB | OFFICIAL: Sensitive - NSW Cabinet
| [Discipline or Sub-Discipline]- | [12 empty] | PRO | Procurement - Readiness for Market (IAG Gate 3) | M040 | Property Acquisition | [6 empty] | #REF! | 01 | [13 empty] | #REF! | 01 |  |  |  |  | Technical | CO | Communication | CV | Civil & structures | Technical | AR | ID | Interior Design | BOM | Bill of Materials | [7 empty] | SG |  |  | D | PUBLISHED | S3 | FOR REVIEW AND COMMENT | Triggers review workflow in Doc Suite | REV-RNC | Released with no comments (no outstanding comments or only minor comments to be updated in the next milestone |  | WG04 | Commissioning | WG04 - Commissioning | [5 empty] | OFF-SEN-LEG | OFFICIAL: Sensitive - Legal
| [Document Type]- | [12 empty] | PRC | Procurement - Procure (IAG Gate 4) | M050 | Third Party Agreements | [6 empty] | #REF! | 02 | [13 empty] | #REF! | 02 |  |  |  |  | Technical | CV | Civil | EL | Electrical | Technical | AR | LA | Landscaping | BOQ | Bill of Quantities | [10 empty] | E | ARCHIVED | S4 | FOR STAGE APPROVAL | Triggers review workflow in Doc Suite. For 2nd or more rounds of review & comment. |  |  |  | WG05 | Management | WG05 - Management | [5 empty] | OFF-SEN-LAW | OFFICIAL: Senstitive - Law Enforcement
| (Serial Number) | [12 empty] | DEL | Delivery - Initial Operations (IAG Gate 5) | M061 | Strategic Business Case | [6 empty] | #REF! | 03 | [13 empty] | #REF! | 03 |  |  |  |  | Business | CX | Construction Management | AR | Architecture & services | Business | CM | CD | Contracts Administration | BRF | Brief | [12 empty] | S5 | AEO CERTIFIED | [12 empty] | OFF-SEN-HIN | OFFICIAL: Sensitive - Health Information
[14 empty] | FIN | Operation - Benefits Realisation (IAG Gate 6) | M071 | Final Business Case | [6 empty] | #REF! | 04 | [13 empty] | #REF! | 04 |  |  |  |  | Business | CY | Community | FL | Fleet | Business | CM | EC | Economic, Financial & Commercial | BRN | Briefing Note / Instruction | [12 empty] | D1 | FOR COSTING | [12 empty] | OFF-SEN-PER | OFFICIAL: Sensitive - Personal
[16 empty] | M101 | Options Design | [6 empty] | #REF! | 01 | [13 empty] | #REF! | 01 |  |  |  |  | Business | DV | Development Management | AR | Architecture & services | Business | CM | FM | Funding & Finance Management | CAL | Calculation | [12 empty] | D2 | FOR TENDER | [12 empty] | OFF-SEN-GOV | OFFICIAL: Sensitive - NSW Government
[16 empty] | M105 | Strategic Design | [6 empty] | #REF! | 02 | [13 empty] | #REF! | 02 |  |  |  |  | Technical | EL | Electrical | AR | Architecture & services | Business | CM | IR | Insurance | CER | Certificate | Including licenses | [11 empty] | D3 | FOR CONTRACTOR DESIGN
[16 empty] | M111 | System Feasibility Review (SFR) | [27 empty] | Business | EN | Environment & Planning | AR | Architecture & services | Business | CM | LG | Legal | CHK | Checklist | [12 empty] | D4 | FOR MANUFACTURE/PROCUREMENT
[16 empty] | M191 | Concept Design Development | [27 empty] | Technical | FE | Fire | SG | Signalling & control | Business | CM | OA | Options Analysis | CLA | Claim / Application | [12 empty] | A1 | NOTE SUBMISSION WITH NO FURTHER COMMENTS
[16 empty] | M201 | System Concept Review (SCR) | [27 empty] | Technical | FL | Fleet Systems & Equipment | CV | Civil & structures | Business | CM | PB | Probity | CNR | Change Request | [12 empty] | A2 | NOTE SUBMISSION WITH FURTHER COMMENTS
[16 empty] | M220 | Concept Design - 20% | [27 empty] | Technical | GN | General | TE | Technology & telecommunications | Business | CM | PR | Procurement | COM | Comment Sheet / Redlines | [12 empty] | A3 | TFNSW CONFIRMED
|  |  |  | In this spreadsheet: | [11 empty] | M250 | Concept Design - 50% | [27 empty] | Technical | HY | Hydraulic | AR | Architecture & services | Business | CM | TC | Transaction Management | CON | Contract | Including project deed, brief, and scope of works | [11 empty] | AA | FOR CONSTRUCTION
|  |  |  | Black Text | These metadata values are governed by TfNSW at the organisation level and will ideally be the same on all projects. Please liaise with the DE Framework team before making any changes. | [10 empty] | M260 | Concept Design - 80% | [27 empty] | Technical | ME | Mechanical |  |  | Technical | CO | ED | External Data Communications | DRG | Drawing | Including DWGs and PDFs | [11 empty] | AB | AS BUILT
[16 empty] | M265 | Concept Design - 100% | [27 empty] | Business | OP | Operation Management | - | - | Technical | CO | IF | Information Systems | DST | Data Sheet | Including room data sheets | [11 empty] | L1 | LEGACY INFORMATION
[16 empty] | M266 | Developed Concept Design (DCD) | [27 empty] | Business | PC | Project Controls | - | - | Technical | CO | IT | Information Technology Network Systems | ECM | Environmental Control Map
[16 empty] | M271 | Reference Design (SCR) | [27 empty] | Business | PM | Project Management | - | - | Technical | CO | KS | Communication Systems | EVL | Evaluation
[16 empty] | M281 | System Design Review (SDR) | [27 empty] | Business | PP | Property | EN | Environmental | Technical | CO | NB | Communications Network Backbone Systems | FLN | File Note
[16 empty] | M285 | Systems Breakdown Review (SBR) | [27 empty] | Business | PT | People & Culture | - | - | Technical | CO | NC | Network Control Communication Systems | FRM | Form | Including confidentiality agreements, design change assessments, design change requests, minor works approvals, purchase orders, check list, inspection and test checklist
[16 empty] | M291 | Preliminary Design Review (PDR) | [27 empty] | Business | SF | Safety | - | - | Technical | CO | WF | Wayfinding | GIS | GIS dataset
|  |  |  | Grey Text | These metadata values are governed by Project level, and will vary between projects. Please discuss with the relevant dataset owners or seek advice from the DE Framework team to agree relevant project parameters. | [10 empty] | M295 | Preliminary Detailed Design (PDD) | [27 empty] | Technical | SG | Signalling & Control | - | - | Technical | CO | WI | Wireless System | GUD | Guide
[16 empty] | M301 | Critical Design Review (CDR) | [27 empty] | Business | SN | Systems Engineering | PP | Property | Technical | CV | EW | Earthworks | IEF | Information Exchange File
[16 empty] | M305 | Detailed Design Review (DDR) | [27 empty] | Technical | ST | Structural | - | - | Technical | CV | FN | Fencing, Barriers and Furniture | IMG | Image / Photo | Including mapping, chart (graphic)
[16 empty] | M311 | Detailed Design - 10% | [27 empty] | Technical | TE | Technology | - | - | Technical | CV | PV | Pavement | INV | Invoice
[16 empty] | M320 | Detailed Design - 20% | [27 empty] | Technical | UT | Utilities | - | - | Technical | CV | RW | Roadworks | ITC | Inspection and Test Check List
[16 empty] | M350 | Detailed Design - 50% | [32 empty] | Technical | CV | SD | Stormwater Drainage | ITP | Inspection and Test Plan
[16 empty] | M360 | Detailed Design - 80% | [32 empty] | Technical | CV | SR | Service Routes | LET | Letter
[16 empty] | M365 | Detailed Design - 100% | [32 empty] | Technical | CV | TR | Track | LST | List
|  |  |  | In this spreadsheet, Grey values are included as examples and should be reviewed for each project. | [11 empty] | M366 | Substantial Detailed Design (SDD) | [32 empty] | Business | CX | FA | Facilities and Amenities | M2D | Model - Two dimensional
[16 empty] | M367 | Final Detailed Design (FDD) | [32 empty] | Business | CX | MB | Mobilisation & Site Establishment | M3D | Model - Three dimensional
[16 empty] | M370 | Final Design Review (FDR) | [32 empty] | Business | CX | SY | Site Security | MAN | Manual
[16 empty] | M381 | Issue for Tender | [32 empty] | Business | CY | CG | Community Engagement | MEM | Memo
[16 empty] | M385 | Pre-AFC | [32 empty] | Business | CY | CU | Customer Experience | MFE | Feasibility Model | Including Estate Master Feasibility Model
[16 empty] | M391 | Accepted For Construction (AFC) | [32 empty] | Business | CY | MD | Media Management | MIN | Meeting Minutes / Agenda
[16 empty] | M392 | Approved For Construction | [32 empty] | Business | CY | SK | Stakeholder Engagement | MKT | Marketing Material
[16 empty] | M395 | Issue For Construction (IFC) | [32 empty] | Business | DV | CL | Cost Planning | NTS | Notice (formal communication) | Including letters, change notices, other notices, proposals and other contractual communication. This code may not exist in TeamBinder, where this is managed as correspondence not documents.
[16 empty] | M400 | Procurement (Contractor Supply) | [32 empty] | Business | DV | FB | Feasibility | PLN | Plan | Including local access plan, network management plan, strategy plan
[16 empty] | M406 | Final Specification Review | [32 empty] | Business | DV | RV | Real Estate and Valuation | PPR | Presentation
[16 empty] | M411 | Construction/Manufacture | [32 empty] | Technical | EL | EB | Earthing, Bonding & Electrolysis | PRG | Programme | Design programme, construction programme
[16 empty] | M420 | Testing & Commissioning | [32 empty] | Technical | EL | EM | Electromagnetic Compatibility (EMC) | PRM | Permit
[16 empty] | M501 | Asset Handover - PCA | [32 empty] | Technical | EL | EZ | Energisation | PRO | Procedure / Policy
[16 empty] | M505 | As Built Review (ABR) | [32 empty] | Technical | EL | HV | HV Electrical Systems | RCD | Record
[16 empty] | M506 | As Built | [32 empty] | Technical | EL | LV | LV Electrical & Lighting Systems | REG | Register | Including transmittals register, drawing register, catalogue, defect list, other lists
[16 empty] | M511 | Defects (Asset Assurance) | [32 empty] | Technical | EL | OT | Overhead Traction Systems | RFI | Request for Information | This is not a doc type in TeamBinder, because RFIs are managed as correspondence. Contractor-CDE may treat these as documents.
[16 empty] | M601 | Asset Assurance Review | [32 empty] | Business | EN | AH | Air Quality | RPT | Report | Including assessment, chart, audit report, non-conformance report, post-implementation report
[16 empty] | M700 | Decommission and Disposal | [32 empty] | Business | EN | CT | Contamination | SCH | Schedule
[50 empty] | Business | EN | DD | DDA Compliance | SDG | Shop Drawing
[50 empty] | Business | EN | EO | Ecology | SHE | Spreadsheet
[50 empty] | Business | EN | ER | Energy & Carbon | SKE | Sketch
[50 empty] | Business | EN | EV | Environmental Management | SOW | Scope of Works
[50 empty] | Business | EN | GE | Geotechnical | SPC | Specification
[50 empty] | Business | EN | LD | Land Use & Management | STD | Standard
[50 empty] | Business | EN | NN | National Construction Code Compliance | STG | Strategy
[50 empty] | Business | EN | NV | Noise & Vibration | SUR | Survey
[50 empty] | Business | EN | PE | Planning Management | TMP | Template
[50 empty] | Business | EN | SB | Sustainability | TST | Test Record
[50 empty] | Business | EN | SM | Spoil Management | VAR | Variation
[50 empty] | Business | EN | SP | Statutory Planning | VIS | Visualization / Animation
[50 empty] | Business | EN | WA | Water Management | WAA | Work Activity Advice
[50 empty] | Business | EN | WD | Wind | WMS | Works Method Statement | Including construction method statement, safe work method statement
[50 empty] | Business | EN | WM | Waste Management | WTY | Warranty
[50 empty] | Technical | FE | EE | Emergency Management
[50 empty] | Technical | FE | FD | Fire Detection System
[50 empty] | Technical | FE | FR | Fire Life and Safety
[50 empty] | Technical | FE | FS | Fire Systems Suppression
[50 empty] | Technical | FL | BG | Bogie
[50 empty] | Technical | FL | BK | Propulsion and Braking
[50 empty] | Technical | FL | CB | Carbody
[50 empty] | Technical | FL | CP | Coupling and Interconnection
[50 empty] | Technical | FL | DO | Doors
[50 empty] | Technical | FL | ES | Energy Supply
[50 empty] | Technical | FL | LR | LRV General
[50 empty] | Technical | FL | LT | Fleet Lighting
[50 empty] | Technical | FL | MU | Aesthetic Design and Mock Ups
[50 empty] | Technical | FL | NI | Network Interface
[50 empty] | Technical | FL | NT | Car Interiors
[50 empty] | Technical | GN | DG | Decommissioning
[50 empty] | Technical | GN | DM | Demolition Plans
[50 empty] | Technical | GN | DY | Durability
[50 empty] | Technical | GN | GL | General Alignment
[50 empty] | Technical | GN | HF | Human Factors
[50 empty] | Technical | GN | PJ | Property Adjustments & Subdivision
[50 empty] | Technical | GN | SU | Surveying
[50 empty] | Technical | GN | SV | Multi-discipline Services
[50 empty] | Technical | GN | TW | Temporary Works
[50 empty] | Technical | HY | CA | Air Systems
[50 empty] | Technical | HY | DR | Drainage (excl. Stormwater)
[50 empty] | Technical | HY | FU | Fuel Systems
[50 empty] | Technical | HY | GA | Gas Systems
[50 empty] | Technical | HY | PU | Plumbing
[50 empty] | Technical | HY | WS | Water Systems
[50 empty] | Technical | HY | WW | Sewer Systems
[50 empty] | Technical | ME | FQ | Fixed Plant & Equipment
[50 empty] | Technical | ME | MQ | Mobile Plant & Equipment
[50 empty] | Technical | ME | VA | HVAC Systems
[50 empty] | Technical | ME | VT | Vertical Transportation
[50 empty] | Business | OP | AI | Asset Information System
[50 empty] | Business | OP | AM | Asset Management
[50 empty] | Business | OP | OC | Operational Control
[50 empty] | Business | OP | OR | Operational Readiness
[50 empty] | Business | OP | RE | RAM Reliability, Availability and Maintainability
[50 empty] | Business | PC | AA | Assurance
[50 empty] | Business | PC | AC | Project Accounting
[50 empty] | Business | PC | AD | Administration
[50 empty] | Business | PC | CC | Configuration Change
[50 empty] | Business | PC | CE | Cost Estimation
[50 empty] | Business | PC | CH | Commissioning, Completions & Handover
[50 empty] | Business | PC | DC | Document and Records Management
[50 empty] | Business | PC | PH | Project Scheduling
[50 empty] | Business | PC | QM | Quality Management
[50 empty] | Business | PC | RM | Risk Management
[50 empty] | Business | PC | RP | Project Reporting Management
[50 empty] | Business | PM | BC | Business Case Management
[50 empty] | Business | PM | CZ | Change Management
[50 empty] | Business | PM | DE | Digital Engineering
[50 empty] | Business | PM | DN | Design Management
[50 empty] | Business | PM | EG | Technical Engineering Management
[50 empty] | Business | PM | HC | Head Contract/s
[50 empty] | Business | PM | PA | Program & Planning Management
[50 empty] | Business | PM | PG | Program Governance & Co-Ordination
[50 empty] | Business | PP | AQ | Acquisitions
[50 empty] | Business | PP | HE | Heritage
[50 empty] | Business | PP | LN | Licenses (Non Software)
[50 empty] | Business | PP | TP | Transport Planning
[50 empty] | Business | PP | VE | Clearance and Vesting
[50 empty] | Business | PT | HR | HR & Training
[50 empty] | Business | PT | WK | Workforce Development
[50 empty] | Business | SF | HD | Hoarding
[50 empty] | Business | SF | HS | Health & Safety
[50 empty] | Business | SF | RA | Rail Safety Accreditation
[50 empty] | Business | SF | SC | Security
[50 empty] | Business | SF | TF | Traffic Management
[50 empty] | Technical | SG | CS | Control Systems
[50 empty] | Technical | SG | GD | Guidance & Delineation Systems
[50 empty] | Technical | SG | NS | Navigation Systems
[50 empty] | Technical | SG | SE | Signalling Systems
[50 empty] | Technical | SG | TT | Intelligent Transport Systems
[50 empty] | Business | SN | CF | Configuration Management
[50 empty] | Business | SN | RQ | Requirements Management
[50 empty] | Business | SN | SI | System Integration
[50 empty] | Technical | ST | BR | Bridge Structures
[50 empty] | Technical | ST | BS | Building Structures
[50 empty] | Technical | ST | IS | Interchange (Station, Stop & Wharf) Structures
[50 empty] | Technical | ST | MS | Miscellaneous Structures
[50 empty] | Technical | ST | OS | Overhead & Support Structures
[50 empty] | Technical | ST | RS | Retaining Structures
[50 empty] | Technical | ST | TU | Tunnel Structures
[50 empty] | Technical | TE | CN | Condition Monitoring System
[50 empty] | Technical | TE | HW | Hardware
[50 empty] | Technical | TE | IM | Instrumentation and Monitoring
[50 empty] | Technical | TE | PI | Passenger Information System
[50 empty] | Technical | TE | SS | Security Systems
[50 empty] | Technical | TE | SW | Software
[50 empty] | Technical | TE | TA | Traffic Safety Systems
[50 empty] | Technical | TE | TI | Traffic Information Systems
[50 empty] | Technical | TE | TK | Ticketing Systems
[50 empty] | Technical | TE | TM | Traffic Monitoring Systems
[50 empty] | Technical | TE | TY | Traffic Regulatory Systems
[50 empty] | Technical | UT | UC | Communications
[50 empty] | Technical | UT | UD | Drainage
[50 empty] | Technical | UT | UE | Electricity
[50 empty] | Technical | UT | UF | Fire service
[50 empty] | Technical | UT | UG | Gas
[50 empty] | Technical | UT | UI | ITS
[50 empty] | Technical | UT | UN | Unidentified services
[50 empty] | Technical | UT | UP | Petroleum products
[50 empty] | Technical | UT | US | Sewer
[50 empty] | Technical | UT | UW | Water

## Standard Version Control
Standard Version Control
Owner: | Workstream Specialists
Authoriser: | Senior Manager Digital Engineering Governance
Approver: | Director Digital Twin Integration
Uniclass Tables: Versions and Release Dates
Table | Version | Release Date | Updated/ Reviewed Date | Group
Co Complexes | 1.15 | 2022-04-25 | 2022-07-31 | Location Classification
EF Elements/ functions | 1.11 | 2022-04-25 | 2022-07-31 | Asset Classification
En Entities | 1.24 | 2022-04-25 | 2022-07-31 | Location Classification
Pr Products | 1.26 | 2022-04-25 | 2022-07-31 | Asset Classification
SL Spaces/ locations | 1.23 | 2022-04-25 | 2022-07-31 | Location Classification
Ss Systems | 1.26 | 2022-04-25 | 2022-07-31 | Asset Classification
TfNSW Standard Data: Versions and Release Dates
Table | Version | Release Date | Updated/ Reviewed Date
Asset Status | ASA v1.8 | 28/01/2021 | 2022-11-29
Contract Types | ver 4.0 | 16/11/2020 | 2022-11-29
Coordinate Systems | ver 4.2 | 30/09/2021 | 2022-11-29
Disciplines | ver 4.1 | 15/11/2021 | 2022-11-29
Document Type | ver 4.0 | 16/11/2020 | 2022-11-29
Drawing Type | ver 0.1 | 16/11/2020 | 2022-11-29
iNSW Project Phases | ver 4.0 | 16/11/2020 | 2022-11-29
Originators | ver 4.36 | TBA | 2022-11-29
Project Milestones | ver 4.1 | 25/02/2022 | 2022-11-29
Review Status | ver 4.1 | 18/11/2022 | 2022-11-29
Security Classification | ver 5.0 | 29/06/2021 | 2022-11-29
State | ver 4.0 | 16/11/2020 | 2022-11-29
Sub-Disciplines | ver 4.3 | 30/08/2022 | 2022-11-29
Suitability | ver 4.0 | 16/11/2020 | 2022-11-29
Work Package Groups | ver 4.2 | 24/03/2022 | 2022-11-29
Work Type (Location) | ver 4.0 | 16/11/2020 | 2022-11-29
Work Type (Work Package) | ver 4.0 | 16/11/2020 | 2022-11-29
For queries regarding this document,
please email the Digital Engineering team at
Digital.engineering@transport.nsw.gov.au
or visit www.transport.nsw.gov.au/digitalengineering