## Information for users
Key information
This council cost estimating tool has been created to assist councils in applying for projects under the new Road Safety Program as well any future road safety programs.
Councils are still required to develop their base estimates utilising their own estimating systems and tools
This tool allows Councils to summarise their estimates and submit a project cost estimate in a consistent manner
This tool is mandatory, as it will be used to facilitate the estimate review and assessment process by TfNSW
The Cost Estimate Summary provides standardised summary items for assessment and comparison purposes and improved visibility and clarity of estimated contingency levels that may be applied to the project estimate
Instructions to complete the template:
1. Council to prepare their project estimate using their own estimating system and tools. (The Council Estimate should be developed to the appropriate level of detail based on the phase of the project and current knowledge)
2. Open the [Cost Estimate Summary] tab. (NOTE: this is the primary working sheet)
Cost Estimate Summary tab
3. (Cell A1) Insert Council Logo or identifier if appropriate
4. (Cell A2) Enter the Project Name
5. (Cell A3) Enter the Program Name
6. (Cell A4) Enter the Project Location
7. (Cell A5) Enter the Project Suburb
8. (Cell A7) Enter the Type/Level of the Project Estimate (i.e. Strategic, Concept, Detailed, etc)
9. (Cell G2) Enter the current date
10. (Cell G3) Enter the Safer Roads Portal project ID (i.e. Project-XXXX)
11. (Cell G4) Enter the Council name
12. (Cell H7) Enter the expected/estimated Duration for the Construction Period
13. Complete the Project Cost Estimate section - this requires input into cells in Columns D, E, F as relevant (Rows 10 to Row 62 only)
14. Using details from the Council's project estimate, update the Quantity, Unit and Rate for each item that is relevant to the project
15. NOTE: Do not delete or overwrite the SUBTOTAL formulas in Cells G11 and G25
16. NOTE: Cells G12, G14, G15, G23, G24, G62 contain formula that may be used to assist in determining costs for these items, alternatively the formula in these cells can be deleted or overwritten by Council by using values determined in their estimate
17. Complete the Contingency for estimates section - this requires input into the highlighted cells in Columns H as relevant (Cells H79; H82; H88; H90; H92; H98 only)
18. Refer to the Notes beneath the Contingency table for guidance on whether to apply an increased or decreased contingency value
19. Consider each Task/activity identified in the table. Determine the appropriate level of contingency that should be applied to each Task/activity Use the Activity Comments, the Yes/No (increase/decrease) suggestions and the % values associated to the Task as guidance in determining the appropriate contingency % to be applied
20. It is recommended to Highlight the appropriate Yes/No cell that was used to justify the contingency % and make comments to support selection. (Example screenshot below)
21. (Cell H79) Enter the appropriate contingency value based on risk and confidence levels at the current time
22. (Cell H82) Enter the appropriate contingency value based on risk and confidence levels at the current time
23. (Cell H88) Enter the appropriate contingency value based on risk and confidence levels at the current time
24. (Cell H90) Enter the appropriate contingency value based on risk and confidence levels at the current time
25. (Cell H92) Enter the appropriate contingency value based on risk and confidence levels at the current time
26. (Cell H98) Enter the appropriate contingency value based on risk and confidence levels at the current time
27. Check that the Total Contingency Value (Cell H101) has transferred correctly to Cell (F64)
Council approval tab
28. Check that Project Description; Program ID Number; Council Name; Date; and estimate values have correctly transferred from the [Cost Estimate Summary] tab.
29. (Cell C2) Check that Project Description has transferred correctly from the [Cost Estimate Summary] tab. (Note: that this is a combined Project Name and Program name)
30. (Cell C3) Check that Program ID Number has transferred correctly from the [Cost Estimate Summary] tab.
31. (Cell F3) Check that Council Name has transferred correctly from the [Cost Estimate Summary] tab.
32. (Cell C4) Use the Dropdown selection to select "Federal", "State", or "Joint Federal & State"
33. (Cell F4) Enter whether delivery will be undertaken by Council Resource or Contract
34. (Cell C5) Enter brief details of the basis for the estimate, such as scope, inclusions, exclusions, etc (or refer to other details provided in Council Estimate)
35. (Cell C6) Use the Dropdown selection to select "Strategic", "Concept", or "Detailed"
36. (Cell F6) Check that date has transferred correctly from the [Cost Estimate Summary] tab.
37. (Cell C7) Check that P50 cost estimate value has transferred correctly from the [Cost Estimate Summary] tab.
38. (Cell D7) Check that value has transferred correctly from the [Cost Estimate Summary] tab.
39. (Cell F7) Check that P50 cost estimate has transferred correctly from the [Cost Estimate Summary] tab.
40. (Cell G7) Check that value has transferred correctly from the [Cost Estimate Summary] tab.
41. (Cell C8) Check that P90 cost estimate has transferred correctly from the [Cost Estimate Summary] tab.
42. (Cell D8) Check that value has transferred correctly from the [Cost Estimate Summary] tab.
43. (Cell F8) Check that P90 cost estimate has transferred correctly from the [Cost Estimate Summary] tab.
44. (Cell G8) Check that value has transferred correctly from the [Cost Estimate Summary] tab.
45. Council Estimate Preparation - Enter the name and position of the Council Representative that prepared the Estimate plus sign and date form
46. After completing the entire form, upload this document as the estimate for the file type in the Safer Roads Portal when completing the project nomination form.

## Cost Estimate Summary
Sidling Hill |  |  |  |  | Current Date: | 2023-03-07
Safety Works |  |  |  |  | Program ID: | 1234
62.863km to 68.725km North of Tamworth, Segments 1660-1700 |  |  |  |  | Council Name: | Regional City Council
Project Cost Estimate | [5 empty] | Construction Duration: | 43 | **Ensure Construction duration is updated appropriately
Description |  |  | Quantity | Unit | Cost |  |  | Comments
[5 empty] | Rate | Amount | %
Costs to date | [5 empty] | 0 | 0%
Infrastructure development |  |  | 88210 | m2 | 25.1105 | 2215000 | 16.91%
Project management |  |  |  |  | 6% | 742000 | 5.664%
Community consultation/engagement | [5 empty] | 20000 | 0.1527%
Concept development |  |  |  |  | 4% | 432000 | 3.298%
Detailed design & documentation |  |  |  |  | 6% | 647000 | 4.939%
Survey | [5 empty] | 0 | 0%
Geotechnical assessment | [5 empty] | 0 | 0%
Environmental assessment | [5 empty] | 50000 | 0.3817%
Biodiversity offsets | [5 empty] | 0 | 0%
Road safety audit | [5 empty] | 0 | 0%
Safe systems assessment | [5 empty] | 0 | 0%
Funding acknowledgement signage | [5 empty] | 0 | 0%
Property acquisition |  |  |  | m2 | 0 | 0 | 0%
Utility services |  |  |  |  | 3% | 324000 | 2.473%
Infrastructure construction |  |  | 88210 | m2 | 122.1744 | 10777000 | 82.27%
Construction preliminary/establishment |  |  | 43 | w | 32302.3256 | 1389000 | 10.6%
Property adjustments |  |  |  | ea | 0 |  | 0%
Drainage |  |  | 11720 | m | 37.2014 | 436000 | 3.328%
Clearing and grubbing |  |  |  | ha | 0 | 185000 | 1.412%
Clear zone adjustments (trees, fencing) |  |  |  | m | 0 |  | 0%
Earthworks |  |  | 88210 | m2 | 19.8617 | 1752000 | 13.37%
Haulage and tipping / waste costs | Haulage and tipping / waste costs | Haulage and tipping / waste costs |  | m3 | 0 |  | 0%
Pavements - concrete |  |  |  | m2 | 0 |  | 0%
Pavements - flexible |  |  | 88210 | m2 | 38.7711 | 3420000 | 26.11%
Pavements - high friction seal |  |  |  | m2 | 0 |  | 0%
Pavements - other seal |  |  |  | m2 | 0 |  | 0%
Pavements - shoulder sealing |  |  |  | m2 | 0 |  | 0%
Structures - bridges, tunnels, retaining walls |  |  |  | m2 | 0 |  | 0%
Facilities, finishing works |  |  |  | m | 0 |  | 0%
Rest areas amenities (toilets, shelters, bins, tables) | Safety barrier | Safety barrier |  | ea | 0 |  | 0%
Safety barrier - install new safety barrier | Safety barrier | Safety barrier | 2468 | m | 232.9822 | 575000 | 4.389%
Safety barrier - install new terminal/s | Safety barrier | Safety barrier |  | ea | 0 |  | 0%
Safety barrier - removal of safety barrier and/or terminal/s | Safety barrier | Safety barrier |  | ea | 0 |  | 0%
Pedestrian fencing and other fencing | Pedestrian fencing and other fencing | Pedestrian fencing and other fencing |  | m | 0 |  | 0%
Concrete medians and islands | Concrete medians and islands | Concrete medians and islands |  | m2 | 0 |  | 0%
Kerb, gutter, kerb blisters, kerb ramps, paths | Kerb, gutter, kerb blisters, kerb ramps, paths | Kerb, gutter, kerb blisters, kerb ramps, paths | 2790 | m | 592.1147 | 1652000 | 12.61%
Raised threshold (raised pedestrian crossing, raised safety platform at intersection) | Raised threshold (i.e. raised pedestrian crossing, raised safety platform at intersection) | Raised threshold (i.e. raised pedestrian crossing, raised safety platform at intersection) |  | ea | 0 |  | 0%
Signage & guideposts (advance warning, curve advisory markers, intersection, road features) | Signage & guideposts (i.e. advance warning, CAMs, intersection, road features) | Signage & guideposts (i.e. advance warning, CAMs, intersection, road features) | 22 | ea | 3090.9091 | 68000 | 0.5191%
Line marking (thermoplastic, audio-tactile, transverse) | Line marking (i.e. thermo, audio-tactile, transverse) | Line marking (i.e. thermo, audio-tactile, transverse) | 28100 | m | 5.0534 | 142000 | 1.084%
Landscaping | Landscaping | Landscaping |  | m2 | 0 |  | 0%
Other (if no relevant category listed, provide details of item in comments column) | Other (if no relevant category listed, provide details of item in comments column) | Other (if no relevant category listed, provide details of item in comments column) |  | item | 0 |  | 0%
Traffic management & temporary works |  |  | 43 | w | 19255.814 | 828000 | 6.321%
Signal, sign, ITS control |  |  |  | item | 0 |  | 0%
Traffic signals (hardware, software, cabling, lanterns) | Traffic signals (hardware, software, cabling, lanterns) | Traffic signals (hardware, software, cabling, lanterns) |  | ea | 0 |  | 0%
ITS signage (vehicle activated signage) | ITS Signage (i.e. Vehicle Activated Signage) | ITS Signage (i.e. Vehicle Activated Signage) |  | ea | 0 |  | 0%
Street lighting | Street Lighting | Street Lighting |  | ea | 0 |  | 0%
Environmental measures |  |  | 43 | w | 1232.5581 | 53000 | 0.4046%
Biodiversity offsets |  |  | 1 | item | 277000 | 277000 | 2.115%
Public utility adjustment |  |  |  | item | 0 |  | 0%
Supplementary items |  |  |  | item | 0 |  | 0%
Other (if no relevant category listed, provide details of item in comments column) | Other (if no relevant category listed, provide details of item in comments column) | Other (if no relevant category listed, provide details of item in comments column) |  | item | 0 |  | 0%
Finalisation |  |  |  |  | 1% | 108000 | 0.8244%
Base Cost Estimate |  |  | 88210 | m2 | 148.5092 | 13100000 | 100%
Inherent & contingent risk contingency |  |  |  |  | 70% | 9170000 | 70%
P90 Current Cost Estimate |  |  | 88210 | m2 | 252.4657 | 22270000 | 170%
Outturn risk contingency |  |  | 2024 | 1 | 15% | 3341000 | 25.5%
P90 Outturn Cost Estimate |  |  | 88210 | m2 | 290.3412 | 25611000 | 195.5%
P50 Current Cost Estimate |  |  | 88210 | m2 | 190.0918 | 16768000 | 128%
P50 Outturn Cost Estimate |  |  | 88210 | m2 | 205.2488 | 18105000 | 138.2%
Contingency for Estimates
Contingency for Strategic Estimates that have been derived using TYPICAL rates such as the ones indicated below should be in the range of 40-70% depending on the confidence and reliability of the of the information used in preparing the estimate. Please note that the estimating manual recommends a range of 35-70%, the 35-40% should be used only if the project has been advanced to concept but for some reason is titled strategic. While the suggested values are based on Strategic Estimates, the applicant can assign much lower contingency values against the task/activity (or even 0%, if no contingency is required). Any number (from 0% to 100%) can be assigned to the contingency value in the table. The table simply adds all contingencies assigned to a total amount at the bottom One way to derive a contingency % is by testing the reliability and confidence there is in different aspects of the information used to generate the estimate:
** Enter contingency value (%) in Gold highlighted cells below
Task/activity | Comments |  |  | Highly confident and reliable | Reasonably confident and reliable | Not confident and not reliable | Contingency | Comments
Project scope | • Is it well defined? | No↑ | Yes↓ | 9% | 12% | 15% | 15%
| • Is there room to vary the works? | No↓ | Yes↑
| • Are there many options? | No↓ | Yes↑
Risks | • Are there significant risks with this Project? No↓Yes↑ | No↓ | Yes↑ | 9% | 12% | 15% | 15%
▪ Political
▪ Community
▪ Technical
▪ Financial
| • Has a detailed risk analysis been undertaken? | No↑ | Yes↓
Constructability | • Has a constructability review been under taken? | No↑ | Yes↓ | 6% | 8% | 10% | 10%
| • Is constructability a problem? | No↓ | Yes↑
Key dates | • Are the Projects dates known? | No↑ | Yes↓ | 3% | 4% | 5% | 5%
| • Is the project planned for the distant future? | No↓ | Yes↑
Information | • Has any investigation been undertaken (include desk top studies)? | No↑ | Yes↓ | 9% | 12% | 15% | 15%
▪ Geotechnical
▪ Heritage
▪ Environmental
▪ Technical
▪ Hydraulic
Length of the project | • Is the project short? | No↓ | Yes↑ | 4% | 7% | 10% | 10%
▪ <1km – short project
▪ >25km – long project
[6 empty] | Total: | 70%
Notes: | • No↓ denotes that if the answer is No, decrease contingency.
• No↑ denotes that if the answer is No, increase contingency.
• Yes↑ denotes that if the answer is Yes, increase contingency.
• Yes↓ denotes that if the answer is Yes, decrease contingency.
If it is required to project the prices into the future, use an escalation factor:
• During construction, adopt a 6% per year linear escalation.
• For time frames of 0-5 years into the future, adopt a 10% per year linear escalation prior to construction
• For time frames in excess of 5 years into the future, adopt a 15% per year linear escalation prior to construction.
References:
http://home.rta.nsw.gov.au/tools/techinfo/documents/ilcms/op_manuals/ilc-est-m-001.pdf
https://home.transport.nsw.gov.au/documents/sppreview/77263577-4df4-4e04-913c-cb062a702378
http://home.rta.nsw.gov.au/tools/techinfo/documents/ilcms/tp0/ilc-mi-tp0-601-g02.pdf
https://km.rms.nsw.gov.au/confluence/display/public/IP/Minor+projects+procedure
https://investment.infrastructure.gov.au/about/funding_and_finance/cost_estimation_guidance.aspx
.
- These formulas in the Outturn risk contingency can be manually adjusted by Councils to reflect an appropriate Outturn risk contingency for the project.
- Alternatively the formula can be deleted and a specific amount (% number) can be manually entered into the cell to reflect an appropriate amount
- As Outturn risk is project dependant and related to external factors, it may be more appropriate to have Councils manually update this as a preferred approach, rather than relying on a pre-defined formula anyway
Construction insurance
TfNSW (Program Managers, etc) will need to determine if construction insurance costs are required to be visibly displayed in an estimate summary.
- If visibility to TfNSW is required, simply include the cost in the “Other” Pay Item that is already included in the Estimate Summary and add a comment that the amount is for Construction Insurance, or any other costs not covered by the predefined category items. - Alternatively Councils can incorporate insurance costs into their estimates and spread the costs across other pay items (i.e. incorporate costs into the rates or other items). Handling Differing Items Under the Same Category For example, if a project involves a heavy vehicle rest area with a toilet block and three bins, the simplest way would be to include the Rest Area as “each” as defined in the Item and then Councils include some details in the comments (such as No. bins, toilet block, etc)
Costs to date will need to be input by council

## Council approval
Project description | Sidling Hill - Safety Works
Safer Roads Portal ID number | 1234 |  | Council Name | Regional City Council
Funding source | State |  | Delivery method | Direct Delivery
Scope description | The estimate is based on: > Sketch plans version 01 dated 01-Feb-23 > Route strategy Jun-22
Estimate status | Strategic |  | Date | 2023-03-07
P50 cost estimate (current $) | 16768000 | 2023-03-07 | P50 cost estimate (outturn $) | 18105000 | 2024
P90 cost estimate (current $) | 22270000 | 2023-03-07 | P90 cost estimate (outturn $) | 25611000 | 2024
Council estimate preparation |  | I have reviewed the project estimate, including the project scope definition, risk register, project cost and schedule reports, and confirm the estimate is prepared in accordance with the relevant council estimating procedure.
|  | Name: |  | Signed: | Date:
Position:
Council estimate recommendation |  | I have reviewed the project estimate including the basis of estimate report, project scope definition and estimate assumptions, and recommend the estimate for concurrence and approval.
|  | Name: |  | Signed: | Date:
Position:
Estimate approval
for infrastructure projects

## Feedback (hidden)
1 | It is worth including an automatic calculation or manual input within the estimate to include Construction Insurances. Not sure if this is mandatory as part of road safety projects, but has been an issue on FLR/FCB programs with guidelines stating that Councils should be taking out insurances but this doesn’t always occur.
2 | Row 66 – Outturn risk contingency. Is this meant to represent the ‘escalation factor’ as outlined in rows 108-111, because this defines an escalation of 6% per year for construction unless project projects into 5+ years. However, the auto-calc in cell F66 is showing 15% escalation for a project that is only 43weeks long (less than one year). This formula needs to be checked.
3 | Rows 74-100 - Based on the parameters for the contingency section it calculates a minimum contingency of 40% to maximum of 70%. This is fine for a ‘Strategic Estimate’, but is high for both Concept and Detailed estimates and in particular for simple projects. It might be possible to modify contingency parameters automatically (as per Project Services estimating guide) based on what time of estimate Council are supplying; Strategic, Concept or Detailed. For example, drop box at top of estimate summary selects the ‘type’ of estimate, which then automatically inputs the parameters for that type of estimate in rows 79-100
4 | There is info for contingency for strategic estimates. What about projects that are at concept or detailed design stage? Can clarity be given regarding anticipated contingency percentages for more advanced projects?
5 | There are often situations where Council is proposing to partially fund a project. For example, they might want to take advantage of the opportunity to also undertake some road rehabilitation work at the same time as some curve widening or other safety treatments. We need to be sure that there is no contingency added to any project components that are being paid for by Council – they should be covering the contingency for the items they’re paying for. I’ve attached a good example of this issue – you’ll note the main project component was a large reseal (at their expense) and a comparatively small safety component. They included the reseal cost in the estimate total (so it was included in the contingency) but only offered to pay the pre-contingency amount – so the amount they were seeking included 182k in contingency for the ineligible reseal component. Despite the reseal being the main project, they were not looking to cover any portion of the project management, traffic management, site preliminary costs, etc., even though these would have been mainly attributed to the large reseal works proposed.
6 | What is the process for differing items under the same category. For example, say it’s a heavy vehicle rest area project that includes a toilet block and three bins. Do they duplicate row 40 to have a row for the toilet block and one for the bins, or do they just leave columns D, E and F blank and populate column G. Ditto for all categories that include multiple different items.
7 | Regarding how user-friendly the instructions are – have you trialled it on any Council staff, or Transport staff who recently came from Council. Might be good to run it by someone like Nathan Murphy (works in Transport, but previously worked at BMCC)?